## NaSARRI Q1 REPORT
PARI | Budget Category/Funding Source | Annual Plan & Budget 2018-2019 | [5 empty] | Quarter 1 report |  |  |  |  | Quarter 2 report | [5 empty] | Quarter 3 report | [5 empty] | Quarter 4 report
PARI | Funding Source | Program/Directorate | Projects/Units (A, B, etc) | Vote Function Output | Annual Key Activities | Annual Outputs | Annual Budget ('000') | Interim or Final Outputs | Interim or final output cummulative | Budget ('000') | expenses ('000') | Remarks | Interim or Final Outputs | Budget | Interim or Final Outputs Actual | Interim or final output cummulative | Releases/expenses ('000') | Remarks | Interim or Final Outputs | Budget | Interim or Final Outputs Acuta | Interim or final output cummulative | Releases/expenses ('000') | Remarks | Interim or Final Outputs | Budget | Interim or Final Outputs Acuta | Interim or final output cummulative | Releases/expenses ('000') | Remarks
| DEVELOPMENT | Cotton programme | Development of cotton varieties with long fibres, tolerant to drought, major insect pests and wilt diseases | Generation of Agricultural Technologies | Preliminary evaluation of strain on station and on farm | 15 strain lines evaluated on station and 2 other locations (Lira and Arua) for yield, fibre quality attributes | 26814.2 | 4 trials established in 4 sites (Serere, Lira, Arua and Kasese) | Non | 6273 | 0 | Funds were not available | 1st data set on agronomic parameters (squaring, flowering)collected | 6270.6 |  | 1st data set on agronomic parameters (squaring, flowering) collected | 0 | Funds were not available | 2nd data set (boll burst, plant height) collected | 8000 | planting done and data collected |  | 8000 | No funds | Post harvest data collected. Technical report on performance written | 6270.6
[5 empty] | 2210020 | Workshops & seminars | #REF! | Workshops & seminars | Non | 3606 | 0 | Funds were not available | Workshops & seminars | 3604 |  |  | 0 | Funds were not available | 2240060 | 4000 | Agric supplies |  | 8000 |  | Workshops & seminars | 3604
[5 empty] | 2240060 | Agricultural supplies | 2249393.2 | Agricultural supplies | Non | 2667 | 0 | Funds were not available | Agricultural supplies | 2666.6 |  |  | 0 | Funds were not available | [6 empty] | Agricultural supplies | 2666.6
|  | Dry lands grain legumes programme | Development of drought tolerant and early maturing greengram varieties and integrated crop management options that increase productivity |  | Conducting greengram/cereal intecropping on-farm trials | 2. Information on apprpriate greengram intercropping system that increase productivity generated | 51124.6 | 4 on-farm trials established in Kumi and Alebtong and genotypes with drought tolerant traits identify | 2 on-farm trials established in Kumi and Alebtong and genotypes with drought tolerant traits identify | 6008.6 | 4500 | Activity done but not complete as expected in quarter one | 4 on-farm trials established in Kumi and Alebtong districts and data on growth attributes collected and analyzed | 6008 | 2 on-farm trials established in Kumi and Alebtong and genotypes with drought tolerant traits identify | 2 on-farm trials established in Kumi and Alebtong and genotypes with drought tolerant traits identify | 5500 | Activity done but not complete as expected in quarter one | Data on yield attributes from 4 on-farm trials collected and analyzed | 33100 | 4 on-farm trials established in Abim and Katakwi and genotypes with drought tolerant traits identify | Activity done but not complete as expected in quarter two | 33100 | No funds | 4 on-farm trials established in Abim and Katakwi and genotypes with drought tolerant traits identify | 6008
[5 empty] | 2210020 | Workshops & seminars | 19362 | Workshops & seminars | Non | 3604 | 0 |  | Workshops & seminars | 3604 |  |  |  |  | 2210020 | 8550 | workshop and seminar |  | 17100 |  | Workshops & seminars | 3604
[5 empty] | 2240060 | Agricultural supplies | 11212.6 | Agricultural supplies |  | 2404.6 |  |  | Agricultural supplies | 2404 |  |  |  |  | 2240060 | 4000 | Agric supplies |  | 16000 |  | Agricultural supplies | 2404
|  | Dry lands cereals | Participatory genetic improvement and promotion of high grain yield, ergot resistance and other desirable attributes for pearl millet |  | Preparing articles on results from project activities | Publication of research results on project activities (production and socioeconomics) | 12811.8 | printing books about pearl millt journal articles | Non | 4270.6 | 0 | Funds were not available | printing booklets about pearl millet utilisation and Journal article written on ergot and smut management technologies | 4270.6 |  |  | 0 | Funds were not available | [7 empty] | 4270.6
[5 empty] | 2210020 | Workshops & seminars | #REF! | Workshops & seminars | Farmers trained on the farm trials established in Kumi and Alebtong and genotypes with drought tolerant traits identify | 2604 | 3500 | Activity was executed to 100% | Workshops & seminars | 2604 | Farmers trained on the farm trials established in Kumi and Alebtong and genotypes with drought tolerant traits identify | Farmers trained on the farm trials established in Kumi and Alebtong and genotypes with drought tolerant traits identify | 2604 |  | Farmers trained on the farm trials established in Alebtong and genotypes with drought tolerant traits identify | 8550 |  |  | 8550 |  | Workshops & seminars | 2604
[19 empty] | Workshops & seminars |  |  |  | 8550
[5 empty] | 2240060 | Agricultural supplies | 6666.4 | Agricultural supplies | Farmers trained on the farm trials established in Kumi and Alebtong and genotypes with drought tolerant traits identify | 1666.6 | 2500 | Activity was executed to 100% | Agricultural supplies | 1666.6 | Farmers trained on the farm trials established in Kumi and Alebtong and genotypes with drought tolerant traits identify | Farmers trained on the farm trials established in Kumi and Alebtong and genotypes with drought tolerant traits identify | 1700 |  |  | 1666.6 |  |  | 8000 |  | Agricultural supplies | 1666.6
[19 empty] | Agricultural supplies | 1667 |  |  | 8000
|  | SUB-TOTAL Generation of agricultural technologies |  |  |  |  | 90750.6 |  |  | 16552.2 | 10500 |  |  | 16549.2 | [5 empty] | 41100 | [5 empty] | 16549.2
|  | NaSARRI Administration | NaSARRI Administration | Research extension interface promoted and strengthened |  |  | 8800 |  | ICT facilities procurement to support instiyute research works on disseminating materials | 2200 | 2200 | Complete ICT and accessories aquired as required to support research |  | 2200 | Complete ICT and accessories aquired as required to support research | Complete ICT and accessories aquired as required to support research | 2200 |  | Complete ICT and accessories aquired as required to support research | 2200 | ICT accessories procured |  | 5088.863 |  |  | 2200
[5 empty] | 2210060 | Computer & IT services | 72600 | Computer & IT services |  | 2200 |  |  | Computer & IT services | 2200 |  |  |  |  | Computer & IT services | 2200 |  |  | 5088.863 |  | Computer & IT services | 66000
|  | NaSARRI Administration | NaSARRI Administration | Agricultural research capacity strengthened
[5 empty] | Office and ICT Equipment, including Software procured to support research activities in the Institute |  | 35000 | Office and ICT Equipment, including Software procured to support research activities in the Institute | Office and ICT Equipment, including Software procured to support research activities in the Institute | 0 | 9200 |  | Office and ICT Equipment, including Software procured to support research activities in the Institute | 17500 | Office and ICT Equipment, including Software procured to support research activities in the Institute | Office and ICT Equipment, including Software procured to support research activities in the Institute | 9200 |  | Office and ICT Equipment, including Software procured to support research activities in the Institute | 17500 | [5 empty] | 0
[6 empty] | Purchase of Office and ICT Equipment, including Software | 35000 | Purchase of Office and ICT Equipment, including Software |  |  |  |  | Purchase of Office and ICT Equipment, including Software | 17500 |  |  |  |  | Purchase of Office and ICT Equipment, including Software | 17500 |  |  |  |  | Purchase of Office and ICT Equipment, including Software
[5 empty] | Office equipments procured to give a condusive working environment ot staff |  | 30000 | Office equipments procured to give a condusive working environment ot staff | Office equipments procured to give a condusive working environment ot staff | 0 | 7500 |  | Office equipments procured to give a condusive working environment ot staff | 15000 | Office equipments procured to give a condusive working environment ot staff | Office equipments procured to give a condusive working environment ot staff | 7500 |  |  | 15000 | [5 empty] | 0
[6 empty] | Machinery & Equipment | 30000 | Machinery & Equipment |  |  |  |  | Machinery & Equipment | 15000 |  |  |  |  | Machinery & Equipment | 15000 |  |  |  |  | Machinery & Equipment
[5 empty] | Office fixtures procured and fixed to have a good working environment for staff |  | 10000 | Office fixtures procured and fixed to have a good working environment for staff | Office fixtures procured and fixed to have a good working environment for staff | 0 | 2500 |  | Office fixtures procured and fixed to have a good working environment for staff | 5000 | Office fixtures procured and fixed to have a good working environment for staff | Office fixtures procured and fixed to have a good working environment for staff | 2500 |  |  | 5000 | [5 empty] | 0
[6 empty] | Furniture & Fixtures | 10000 | Furniture & Fixtures |  |  |  |  | Furniture & Fixtures | 5000 |  |  |  |  | Furniture & Fixtures | 5000 |  |  |  |  | Furniture & Fixtures
|  | TOTAL DEVELOPMENT BUDGET | [20 empty] | 54739 |  |  | #REF!
NATIONAL SEMI-ARID RESOURCES RESEARCH INSTITUTE - (NaSARRI) | RECURRENT | Dry lands cereals | Development and promotion of drought and Integrated striga management options in sorghum | Generation of agricultural technologies | a) Screening of sorghum germplasm for resistance against stemborer damage Continues. b). Testing the effectiveness of seed dressing insecticides on sorghum seedlings against shootfly damage. | a) Sorghum genotypes resistant / susceptible / tolerant to sorghum stem borers identified. b). Effective seed dressing insecticides against shootflies established onstation. | 6000 | a). Sorghum germplasm characterised and assembled for screening against stemborer screening b). Field experiments to test for effectiveness of seed dressing insecticides conducted onstation. | Non | 1500 | 0 | Funds were not available to implement the activities | Experiments on screening of sorghum germplasm against stemborer established onstation / screenhouse / Laboratory b). Data on the effect of seed dressing insecticides against shootflies collected and analysed | 1500 |  |  |  |  | Field experiments to test for effectiveness of seed dressing insecticides conducted onstation. | 1500 |  |  | 1120 |  | Experiments on screening of sorghum germplasm against stemborer established onstation / screenhouse / Laboratory b). Data on the effect of seed dressing insecticides against shootflies collected and analysed | 1500
[5 empty] | 2270010 | Travel inland | 3000 | Travel inland |  | 750 |  |  | Travel inland | 750 |  |  |  |  | Travel inland | 750 |  | Travel inland | 600 |  | Travel inland | 750
[5 empty] | 2270040 | Fuel, Lubricants & Oils | 3000 | Fuel, Lubricants & Oils |  | 750 |  |  | Fuel, Lubricants & Oils | 750 |  |  |  |  | Fuel, Lubricants & Oils | 750 |  | Fuel, Lubricants & Oils | 520 |  | Fuel, Lubricants & Oils | 750
|  | Dry land grain legumes programme | Development of drought tolerant and early maturing greengram varieties and integrated crop management options that increase productivity |  | Maintaining and cleaning of greengram stores and laboratories | Greengram stores and laboratories well maintained and kept cleaned | 6000 | Greengram stores and laboratories well maintained and kept cleaned | Non | 1500 | 0 | Funds were not available to implement the activities | Greengram stores and laboratories well maintained and kept cleaned | 1500 |  |  |  |  | Greengram stores and laboratories well maintained and kept cleaned | 1500 |  |  | 1500 |  | Greengram stores and laboratories well maintained and kept cleaned | 1500
[5 empty] | 2270010 | Travel inland | 3000 | Travel inland |  | 750 |  |  | Travel inland | 750 |  |  |  |  | Travel inland | 750 |  | Travel inland | 750 |  | Travel inland | 750
[5 empty] | 2270040 | Fuel, Lubricants & Oils | 3000 | Fuel, Lubricants & Oils |  | 750 |  |  | Fuel, Lubricants & Oils | 750 |  |  |  |  | Fuel, Lubricants & Oils | 750 |  | Fuel, Lubricants & Oils | 750 |  | Fuel, Lubricants & Oils | 750
|  | SUB-TOTAL Generation of agricultural technologies |  |  |  |  | 12000 |  |  | 3000 |  |  |  | 3000 | [5 empty] | 3000 | [5 empty] | 3000
NATIONAL SEMI-ARID RESOURCES RESEARCH INSTITUTE - (NaSARRI) | RECURRENT | NaSARRI Administration | NaSARRI Administration | Agricultural research capacity strengthened | Contracted staff |  | 11000 | wages paid to contracted staff | wages paid to contracted staff | 2750 | 2750 |  | wages paid to contracted staff | 2750 | wages paid to contracted staff | wages paid to contracted staff | 2750 |  | wages paid to contracted staff | 2750 | wages paid to contracted staff |  | 2750 |  | wages paid to contracted staff | 2750
[5 empty] | 2111020 | contract casual labour | 11000 | contract casual labour |  | 2750 |  |  | contract casual labour | 2750 |  |  |  |  | contract casual labour | 2750 |  | contract casual labour | 2750 |  | contract casual labour | 2750
[5 empty] | Compound and offices kept clean | At least 14 acres of compound mowed and 12 office blocks cleaned | 4000 | Contracted labor paid | Contracted labor paid | 1000 | 1000 |  | Contract labor paid | 1000 | Contract labor paid | Contract labor paid | 1000 |  | Contract labor paid | 1000 | Contracted labor paid |  | 0 | No funds released | Contract labor paid | 1000
[5 empty] | 2260040 | Sanitation & cleaning | 4000 | Sanitation & cleaning |  | 1000 |  |  | Sanitation & cleaning | 1000 |  |  |  |  | Sanitation & cleaning | 1000 |  |  | 0 | No funds released | Sanitation & cleaning | 1000
[5 empty] | Placement of pullout news supplements in both local and national media, acquistion of airtime to disseminate positive informaation about the Institute activities and achievements | Informed stakeholders maintained and NaSARRI's Corporate Image protected | 5000 | Informed stakeholders maintained, public relations and the institute's corporate image protected. | Informed stakeholders maintained, public relations and the institute's corporate image protected. | 1250 | 1250 |  | Informed stakeholders maintained, public relations and the institute's corporate image protected. | 1250 | Informed stakeholders maintained, public relations and the institute's corporate image protected. | Informed stakeholders maintained, public relations and the institute's corporate image protected. | 1250 |  | Informed stakeholders maintained, public relations and the institute's corporate image protected. | 1250 | Informed stakeholders maintained, public relations and the institute's corporate image protected. |  | 1250 |  | Informed stakeholders maintained, public relations and the institute's corporate image protected. | 1250
[5 empty] | 2210010 | Advertising & public relations | 5000 | Advertising & public relations |  | 1250 |  |  | Advertising & public relations | 1250 |  |  |  |  | Advertising & public relations | 1250 |  |  |  |  | Advertising & public relations | 1250
[7 empty] | 4000 |  |  | 1000 |  |  |  | 1000 |  |  |  |  | Printing & stationery | 1000 | dissemination materials printed |  | 1000 |  |  | 1000
[6 empty] | Printing & stationery | 4000 |  |  | 1000 |  |  |  | 1000 |  |  |  |  | Printing & stationery | 1000 | [5 empty] | 1000
[7 empty] | 1000 |  |  | 1000
[5 empty] | 2210070 | Books, Periodicals & Newspapers | 2000 | Books, Periodicals & Newspapers |  | 1000 | [8 empty] | Telephone bills paid | 1000 | Telephone bills paid |  | 1000
[5 empty] | Telephone bills paid | Telephone bills paid | 6000 | Telephone bills paid | Telephone bills paid | 1000 | 1000 |  | Telephone bills paid | 1000 | Telephone bills paid | Telephone bills paid | 1000 |  |  | 1000 |  |  |  |  | Telephone bills paid | 3000
[5 empty] | 2220010 | Telecommunication | 8000 |  |  | 1000 |  |  |  | 1000 |  |  |  |  | Electricity bills paid | 3000 | Electricity bills paid. |  | 3000 |  |  | 3000
[5 empty] | Utility bills for electricity paid. | Electricity bills paid. | 11000 | Electricity bills paid. | Electricity bills paid. | 3000 | 3000 |  | Electricity bills paid | 3000 | Electricity bills paid | Electricity bills paid | 3000 |  |  | 3000 |  |  |  |  | Electricity bills paid | 2000
[5 empty] | 2230050 | Electricity | 10000 |  |  | 3000 |  |  |  | 3000 |  |  |  |  | Guard & security bills settled | 2000 | Guard & security bills settled |  | 2000 |  |  | 2000
[5 empty] | settlement of security services for the institute | guarding services | 6000 | Guard & security bills settled | Guard & security bills settled | 2000 | 2000 |  | Guard & security bills settled | 2000 | Guard & security bills settled | Guard & security bills settled | 2000 |  |  | 2000 |  |  |  |  | Guard & security bills settled | 0
[5 empty] | 2230060 | Guard & security services | 4000 |  |  | 2000 |  |  |  | 2000 | [6 empty] | three committee meetings conducted |  | 1500 |  |  | 0
[5 empty] | Strategic and operational decisions enhanced | At least four advisory meetings conducted, 16 committee meetings conducted | 1948 | Atleast three committee meetings conducted | three committee meetings conducted | 224 | 3000 |  | Atleast three committee meetings conducted | 224 | Atleast three committee meetings conducted | Atleast three committee meetings conducted | 3000 |  | committee, council and board expenses covered | 1500 | committee, council and board expenses covered |  | 1500
[19 empty] | 2210060 |  | committee, council and board expenses covered |  | 1500
[5 empty] | 2210090 | Welfare & Entertainment | 896 | Welfare & Entertainment | Welfare & Entertainment | 224 | 224 |  | Welfare & Entertainment | 224 | Welfare & Entertainment | Welfare & Entertainment | 224 |  | Welfare & Entertainment | 224 | Institute Welfare & Entertainment activites executed |  | 224
[5 empty] | 2260010 |  | 1184 |  |  | 320 |  |  |  | 320 |  |  |  |  | 2210090 | 224 |  |  | 224 |  |  | 320
[5 empty] | 2260010 | Insurances | 2166 | Institute motor vehicles and motor cycles insured for a year | Institute motor vehicles and motor cycles insured for a year | 320 | 320 |  | Institute motor vehicles and motor cycles insured for a year | 320 | Institute motor vehicles and motor cycles insured for a year | Institute motor vehicles and motor cycles insured for a year | 320 |  |  | 1206 | 5 vehicles services and maintained in a good condition |  | 320 |  | Insurances | 320
[7 empty] | 3618 |  |  | 1206 |  |  |  | 1206 |  |  |  |  | 2260010 |  |  |  | 320 |  |  | 1206
[5 empty] | 2280020 | Maintenance - Vehicles | 5118 | 5 vehicles services and maintained in a good condition | 5 vehicles services and maintained in a good condition | 1206 | 1206 |  | 5 vehicles services and maintained in a good condition | 1206 | 5 vehicles services and maintained in a good condition | 5 vehicles services and maintained in a good condition | 1206 |  |  | 1500 | [5 empty] | 1206
[7 empty] | #REF! |  |  | 1500 |  |  |  | 1500 |  |  |  |  | 2280020 |  | maintainance vehicles |  | 1206 |  |  | 1500
[5 empty] | 2731020 | Incapacity, death benefits and Funeral costs | 6000 |  |  | 1500 |  |  |  | 1500 |  |  |  |  | Incapacity, death benefits and Funeral costs | 1500 |  |  | 1500 |  |  | 1500
[19 empty] | 2731020 |  | Incapacity, death benefits and Funera |  | 1500
|  | TOTAL RECURRENT BUDGET |  |  |  |  | 79720 |  |  | 19930 |  |  |  | 19930 | [5 empty] | 19930
NATIONAL SEMI-ARID RESOURCES RESEARCH INSTITUTE - (NaSARRI) | NTR | NaSARRI Administration | NaSARRI Administration | Agricultural research capacity strengthened | Installation of intercom in offices | Internal communication Improved | 9000 | Procuring of 22 telephone handsets |  | 9000
[5 empty] | 2220030 | Information & communication | 9000 |  |  | 9000
[5 empty] | 16 fire extinguishers procured | fire extinguishers procured | 16000 | 8 fire extinguishers procured |  | 8000 | [8 empty] | 10 fire extinguishers procured | 8000
[5 empty] | 2210120 | Small office equipment | 16000 |  |  | 8000 | [9 empty] | 8000
[5 empty] | Empting of sepetic tanks and repair of broken sewerage pipes and manholes. | Improved disposal of sewerage. | 8000 | Empting of Sepetic Tanks | 1 Sepetic Tanks empted | 2000 | 2000 |  | Repair of broken Sewerage pipes | 2000 | Repair of broken Sewerage pipes | Repair of broken Sewerage pipes | 2000 |  | Repair of manholes | 2000 | manholes repaired around the Institute |  | 1000 |  | Sinking of pit laterines and dust bins | 2000
[5 empty] | 2260040 | Sanitation &cleaning | 8000 |  |  | 2000 |  |  |  | 2000 |  |  |  |  | 2280010 | 2000 |  |  | 1000 |  |  | 2000
[5 empty] | Openning, Digging of drainages and paving works | At least 8 km of drainage system established and fixed | 12000 | At least 2 drainages established | 2 drainages established | 3000 | 3000 |  | At least 2 drainages established | 3000 | At least 2 drainages established | At least 2 drainages established | 3000 |  | At least 2 drainages established | 3000 | 2 drainages established and maintained |  | 1500 |  | At least 2 drainages established | 3000
[5 empty] | 2280010 | civil works | 12000 |  |  | 3000 |  |  |  | 3000 |  |  |  |  | 2280010 | 3000 |  |  | 1500 |  |  | 3000
[5 empty] | Institute and farm raods maintained | At least 8 Km of major institute and farm roads are motorable | 24000 | 3km of Institute roads maintained | 3km of Institute roads maintained | 6000 | 6000 |  | 2km of Institute roads maintained | 6000 | 2km of Institute roads maintained | 2km of Institute roads maintained | 6000 |  | 2km of Institute roads maintained | 6000 | Not done |  | 2500 | No funds | 2km of Institute roads maintained | 6000
[5 empty] | 2280010 | civil works | 24000 |  |  | 6000 |  |  |  | 6000 |  |  |  |  | 2240040 | 6000 |  |  | 2500 |  |  | 6000
[5 empty] | Procurement of TV screen and book shelves for the resource centere | Improved acess to information by our stake holders improved | 6000 | TV screen procured and in use |  | 3000 | [14 empty] | Two bookshelves procured and assembled for use | 3000
[5 empty] | 2210010 | Advertising & public relations | 6000 |  |  | 3000 | [15 empty] | 3000
[5 empty] | Generation of fruit tree seedlings | Fruit tree seedlings generated | 22000 | 2500, mangoe seedlings and 1500 orange seedlings established | 500, mangoe seedlings and 500 orange seedlings established | 11000 | 5000 |  | 2500, mangoe seedlings and 1500 orange seedlings established | 11000 | 2500, mangoe seedlings and 1500 orange seedlings established | 2500, mangoe seedlings and 1500 orange seedlings established | 5000
[5 empty] | 2240060 | Agric. Supplies | 22000 |  |  | 11000 |  |  |  | 11000
[5 empty] | Cassava seed production for NTR | 15 acres of NARO CASS 1 established | 28000 | 15acres openned and planted | 10acres openned and planted | 7000 | 5000 |  | 15 acres weeded and managed | 7000 |  |  |  |  | 15 acres weeded and managed | 7000 | Not done |  | 2464 | No funds | 15 acres weeded and managed | 7000
[5 empty] | 2240060 | Agric. Supplies | 28000 |  |  | 7000 |  |  |  | 7000 |  |  |  |  | 2240060 | 7000 |  |  | 2464 |  |  | 7000
[5 empty] | Staff houses renovated | 4 houses rennovated and maintained | 24800 | 2 house renovated | 2 house renovated | 6200 | 6200 |  | 1 house renovated | 6200 |  |  |  |  | 1 house renovated | 6200 | 2 houses renovated |  | 1550 |  | 1 Staff house renovated | 6200
[5 empty] | 2280010 | civil works | 24800 |  |  | 6200 |  |  |  | 6200 |  |  |  |  | 2280010 | 6200 |  |  | 1550 |  |  | 6200
[5 empty] | Travel Inland | institute activities enhanced through knowledge sharing | 40000 | Atleast three experience sharing and exposure visits conducted |  | 10000 |  |  | Atleast two experience sharing and exposure visits conducted | 10000 |  |  |  |  | Atleast two experience sharing and exposure visits conducted | 10000 | Four exposure visits conducted |  | 6000 |  | Atleast two experience sharing and exposure visits conducted | 10000
[5 empty] | 2270010 | Travel Inland | 40000 |  |  | 10000 |  |  |  | 10000 |  |  |  |  | 2270010 | 10000 |  |  | 6000 |  |  | 10000
[5 empty] | Procurement of tractor drawned mower | Atleast one tractor mower procured | 28000 | Atleast one tractor mower procured |  | 28000 |  |  | Atleast one tractor mower procured
[5 empty] | 2280030 | Maintenance Machinery | 5000 | [6 empty] | 5000
[5 empty] | Procurement of assorted pesticides and simple farm tools | Assorted pesticides and simple farm tools procured | 20000 | Assorted pesticides and simple farm tools procured | Assorted pesticides and simple farm tools procured | 5000 | 5000 |  | Assorted pesticides and simple farm tools procured | 5000 |  |  |  |  | Assorted pesticides and simple farm tools procured | 5000 | pesticides and farm tools procured |  | 5000 |  | Assorted pesticides and simple farm tools procured | 5000
[5 empty] | 2240010 | Medical & vetinary supplies | 20000 |  |  | 5000 |  |  |  | 5000 |  |  |  |  | 2240010 | 5000 |  |  | 5000 |  |  | 5000
|  | SUB-TOTALAgricultural research capacity strengthened |  |  |  |  | 237800 |  |  | 98200 | 32200 |  |  | 50200 | [5 empty] | 47200 | [5 empty] | 42200
|  | TOTAL RECURRENT BUDGET |  |  |  |  | 237800 |  |  | 98200 | 32200 |  |  | 50200 | [5 empty] | 47200 |  |  | 20014 |  |  | 42200
Off- Budget (CDO)
|  | Cotton programme | Development of cotton varieties with long fibres, tolerant to drought, major insect pests and wilt diseases | Generation of agricultural technologies | Regeneration and evaluation of germplasm stocks at NaSARRI | 50 germplasm lines evaluated for agronomic and yield related parameters | 6750 | cotton germplasm stocks retrieved from the National Gene Bank for regeneration | 64 lines retrieved from National Gene Bank planted at NaSARRI | 1688 | 1688 | Good crop vigour though there were incidences of dry spell that was experienced during the reporting period | First agronomic data set collected (square date, flower date) | 1781 | 1st data set ( squaring, 1st flower, and 50% flowering ) collected . Selfing has been done to maintain purity. | preliminary data analysis done on agronomic data sets collected | 1781 |  | 2nd data set collected (boll size, shape, branching patterns, days to boll burst) | 1781 | 2nd data set collected and compileled for analysis |  | 1500 | drought concided with flowering period | Post harvest data collected. (boll weight, Yield and fibre quality) | 1500
[5 empty] | Production of nucleus and foundation seed of BPA 2015A | 1 ton of Nucleus and 10 tons of foundation seed produced | 66750 | 10 acres and 75 acres of land opened for production of Nucleus and foundation seed, respectively | 5 acres and 75 acres of land planted with BPA 2015A for production of nucleus and foundation seed, respectively | 18400 | 18400 | Good crop vigour though there were incidences of dry spell that was experienced during the reporting period | Field maintenance (weeding, rouging, spraying) | 24400 | Roguing of off types done on seed plots | crop has started opening. Harvesting start in Feburary | 24400 | CDO supplimentary budget and payments were done directly to the labourers' phone numbers from CDO Head Office | harvesting and ginning seed cotton | 13475 | harvesting completed. Weighing of seed cotton in progress which will be followed by ginning |  | 3000 | drought concided with flowering of the crop. Expected yield may be less than anticipated | seed grading and delinting | 10475
[5 empty] | Prelimianry evaluation of cotton strains for yield and fibre quality attributes | 15 strain lines evaluated at NaSARRI and on farm sites (Lira, Kasese, Tororo, Nebbi and Adjumani | 24260 | 15 strain lines planted at NaSARRI only. | 15 strain lines planted at NaSARRI | 6640 | 6640 | Good crop vigour though there were incidences of dry spell that was experienced during the reporting period. However, due to lack of funds we were unable to conduct the establishment of field trials in Lira, Kasese, Tororo, Nebbi and Adjumani districts | First data set on agronomic parameters collected | 6060 | 1st agronomic data set (squaring, 1st flowering, 50% flowering) collected | Continuous observation of different agronomic cotton traits is still on-going | 6060 | CDO supplimentary budget data payments were done directly ze the labourers' phone numbers from CDO Head Office | 2nd data set collected (boll size, shape, branching patterns, days to boll burst) | 5480 | data on boll size, shape, branching patterns and days to boll burst collected. Preliminary analysis done. |  | 1500 | Drought affected the trial | harvestng, ginning ad post harvest data colletion. | 6080
[5 empty] | Evaluation of introduced and newly released cotton varieties under different row and intra-row spacings in different cotton zones | Introduced and released cotton varieties evaluated for agronomic stability across different cotton Zones | 19636 | Sufficient seed of different cotton varieties assembled and planted on-station and on-farm sites at least three off-station sites by July 2018 | Seven cotton varieties were planted at three row spacings and two intra-row spacings at NaSARRI, Luuka, Tororo, Oyam and Kiryadongo districts. The varieties were BPA 2015 A, BPA 2015 B and BPA 2002 as a control (all the three from Uganda), and SZ 931Y, QM 301, MS-1 and MS-2 (introduced from Zimbabwe). The row spacings were 80, 90 and 100 cm while intra-row spacings were 30 and 45 cm. | 7900 | 4200 | CDO supported planting but labour for on-station trials and weeding at off-station trials not yet paid | Required agronomic data and harvesting of the cotton from on-station trials accomplished by December 2018 | 3200 |  | Of the seven cotton varieties (BPA 2015 A, BPA 2015 B, BPA 2002, SZ 931Y, QM 301, MS-1 and MS-2) planted at three row spacings and two intra-row spacings at NaSARRI, Luuka, Tororo, Oyam and Kiryadongo districts, MS-2 exhibited very low emergence in all places. Cotton from all sites were harvested and being sorted for weighing, ginning and lint analysis, except the one from Kiryadongo which was stolen from the field. | 2100 | CDO supported all activities including payment of labour for harvesting | Required agronomic data and harvesting of the cotton from on-farm trials accomplished by March 2019 | 11000 |  | Of the seven cotton varieties (BPA 2015 A, BPA 2015 B, BPA 2002, SZ 931Y, QM 301, MS-1 and MS-2) planted at three row spacings and two intra-row spacings at NaSARRI, seed cotton yields for the varieties were 2076.2, 2107.5, 1653.2, 1927.9, 2098.8, 1934.3 and 1448.3 kg/ha respectively. Yields from Luuka, Tororo and Oyam were not yet analyzed while cotton from Kiryadongo was stolen from the field. Ginning was not yet done as the machines were being cleaned and serviced. | 3000 |  | Analysis of cotton fibre characteristics and seed oil and protein contents done on all samples and overall report written by June 2019 | 6072
[5 empty] | Intercropping cotton and cowpeas under different cowpea leaf plucking frequencies | Productivity of cotton/cowpea intercropping systems determined and demonstrated under multi-location trials | 22980 | Planting cotton/cowpea intercropping trials done in at least three sites by September 2018 | Six cotton/cowpea intercropping systems were planted on-station and two systems planted on-farm sites in 12 farmers fields in Oyam and Kiryadongo districts. The on-station trial had treatments where the cowpeas intercropped with cotton had their leaves un-plucked or plucked once, twice, thrice and four times. The on-farm trials had treatments where the cowpeas intercropped with cotton had their leaves either un-plucked or plucked without going into details of frequency. | 5745 | 1950 | CDO supported planting but labour for on-station trials and all activities at off-station trials not yet paid | Collection of all required data on cowpeas done by October 2018 | 5745 |  | From the on-station trial, cowpeas intercropped with cotton where cowpea leaves were un-plucked, plucked once, twice, thrice and four times gave 0.0, 78.3, 387.4, 777.0 and 960.3 kg/ha of cowpea leaves, respectively, and cowpea grain yields of 1883.8, 1302.5, 1291.6, 1144.6, 940.6 and 889.5 kg/ha, respectively. Cotton was picked and being sorted and weighed. Its performance will be reported in the next quarter. Data from on-farm trials have not yet been collected. | 1800 | CDO supported all activities including payment of labour for harvesting | Collection of all required data on cotton and harvesting done by December 2018 | 5745 |  | From the on-station trial, cowpeas intercropped with cotton where cowpea leaves were un-plucked, plucked once, twice, thrice and four times gave 0.0, 78.3, 387.4, 777.0 and 960.3 kg/ha of cowpea leaves respectively, and cowpea grain yields of 1883.8, 1302.5, 1291.6, 1144.6, 940.6 and 889.5 kg/ha, respectively. Intercropping reduced seed cotton yields from the on-station trial. Yields from pure cotton, intercropped with un-plucked cowpeas, with cowpeas whose leaves were plucked once, twice, thrice and four times were 835.0, 136.0, 240.2, 208.2, 194.7 and 138.6 kg/ha. Cotton and cowpea yields were obtained from five farmers but were not yet analyzed. | 2500 |  | A comprehensive report/research paper on intercropping of cotton and cowpeas written by June 2019 for publication in a peer reviewed journal.Up to 50 farmers trained on intercropping of cotton with cowpeas done by June 2019 | 5745
[5 empty] | Enhancing cotton perfomance by application of foliar fertilizers | Effectiveness of foliar fertilizers on cotton determined and demonstrated in multi-locations | 6969 | Planting of trial to test different rates and application frequencies of at least one foliar fertilizer on-station, done by August 2018 | Only one foliar fertilizer (AEROS) was obtained for testing. Two trials were planted at NaSARRI to test three AEROS concentrations (500, 1000 and 1500mls/ha) and three application frequencies (once, twice and thrice), with and without soil-applied NPK and Urea. | 4984 | 0 | All activities done on credit and still waiting for financial support from CDO to clear the debts | Collection of required agronomic data and harvesting accomplished by December 2018 | 1742 |  | Cotton from two trials planted at NaSARRI to test three AEROS concentrations (500, 1000 and 1500mls/ha) and three application frequencies (once, twice and thrice), with and without soil-applied NPK and Urea was picked. Sorting and weighing for analysis is on-going and will be reported in the next quarter. | 1200 | CDO supported all activities including payment of labour for harvesting | Establishment of off-station sites for further testing and demonstration of foliar fertilizers on cotton done by April 2019 | 1742 |  | Cotton from two trials planted at NaSARRI to test three AEROS concentrations (500, 1000 and 1500mls/ha) and three application frequencies (once, twice and thrice), with and without soil-applied NPK and Urea was picked. Yields were generally low from the trials and pre-application of NPK did not improve the situation significantly. Where AEROS was applied twice to cotton without pre-applied NPK, seed cotton yields were 1838.5, 1718.6, 1623.0 kg/ha from rates of 500, 1000 and 1500 mls/ha compared to 1959.9 and 1741.7 where only NPK was applied and the control respectively. | 1000 |  | Training of stakeholders on foliar fertilizers use in cotton done by June 2019. A comprehensive report/research paper on use of foliar fertilizers in cotton written by March 2019 for publication in a peer reviewed journal. | 1742
[5 empty] | Testing various cover crops as alternative sources of soil nutrients for cotton production in Uganda | Effectiveness of cover crops in enhancing soil fertility for cotton determined | 7644 | Collecting of different cover crops from various sources done by August 2018 | Sufficient seed of Mucuna and limited amounts of Crotolaria were obtained for establishment at NaSARRI | 1900 | 0 | We were unable to establish them in the field because of dry spell. Expected to establish them when the rains start this season or first season of the following year | Planting of different cover crops from various sources done on-station by November 2018 | 2100 |  | The cover crops were not planted | 0 | We lacked funds for this activity | Planting of cotton in plots previously under different cover crops done by May 2019 | 3600 |  | The cover crops were not planted |  |  | Collecting and analyzing preliminary data on cotton growth under different cover crops done by June 2019 | 3400
[5 empty] | Promote effective biopesticides and synthetic pesticides in the cotton growing agro-ecologies for the control of major insect pests (lygus bugs, Bollworms and Stainers) in cotton | One effective biopesticides and three synthetic pesticides promoted through demonstrations at on-farms in the cotton growing regions in eastern, northern and western for management of major cotton insect pests | 11100 | Demonstration sites identified and planted with two new pre-released cotton varieties and applied with effective bio-pesticides and synthetic pesticides in eastern, northern and western regions for the control of lygus bugs, bollworms and stainers | Demonstration sites selected as follows; 1 acre at NaSARRI in Serere, 1 acre in Barr subcounty in Lira district, 1 acrea in Balawoli subcounty in Kamuli district and 1 acre Prison Farm in Kasese. Trials planted in the selected sites and data on pest incidence before spraying collected | 1150 | 1100 | CDO supplimentary budget | 1 acre each planted at Kamuli, Lira and Kasese while 5 acres planted at NaSARRI and data on first round of six chemical applications collected(Celite 6,Profenophos 80%,Iticel,Select plus, Quinalphos20%Ec,Profenophos 50%EC) | 2000 | Efficacy data collected on (Celite 6,Profenophos 80%,Iticel,Select plus, Quinalphos20%Ec,Profenophos 50%EC) & work is still in progress |  |  | CDO supplimentary budget and payments were done directly to the labourers' phone numbers from CDO Head Office | Promoting most effective biopesticide and synthetic pesticide through trainings in Serere and Kamuli | 2650 | Data on efficacy, Pest incidence and prevalence, yield and promising application rates collected on Celite 6, Profenophos 80%,Iticel, Select plus, Quinalphos20%Ec,Profenophos 50%EC) | 1 acre of second season planted at Kamuli, 1acre planted at Lira and 5acres planted at NaSARRI and data on second round of six chemical applications collected Celite 6,Profenophos 80%,Iticel,Select plus, Quinalphos20%Ec,Profenophos 50%EC | 2650 | CDO supplimentary budget | Promoting most effective biopesticide and synthetic pesticide through trainings in Lira and Kasese | 3150
[5 empty] | Two biopesticides produced and efficacy tested in the laboratory before massive production | Efficacy of two biopesticcides tested in the laboratory before massive production | 7000 | Pure cultures of metharizium A, Beauvelllia bassiana,obtained and massively produced | Pure cultures of metharizium A, Beauvelllia bassiana obtained | 2000 | 1700 | CDO supplimentary budget | Pure cultures of metharizium A, Beauvelllia bassiana,obtained and massively produced and laboratory efficacy tested. | 2200 | Pure cultures of metharizium A isolated . Cotton boll worm,fall armyworm &Chilo partellus rearing is on going for efficacy testing |  |  | CDO supplimentary budget and payments were done directly to the labourers' phone numbers from CDO Head Office | Pure cultures of metharizium A, Beauvelllia bassiana produced advanced to next generation | 2000 | Data collected on laboratory efficacy of metharhizium A, and Beauvellia basianna collected | Data on field efficacy evaluation of Metharhizium A,and Beauvellia basianna on fall army worm,cotton bollworms generated. | 2000 | CDO supplimentary budget | Preliminary release of pure cultures of metharizium A, Beauvelllia bassiana in the field at NaSARRI, Serere | 800
[5 empty] | Promote effective seed dressing chemicals in cotton growing agro-ecologies for the control of wilts and seedling diseases | Two effective seed dressing chemicals promoted through on-farm demostrations in cotton growing regions in eastern, northern and western for management of wilts and seedling diseases | 8000 | Demonstration sites identified in eastern, northern and western regions and two effective cotton seed dressing chemicals (Cruiser and Maixm) were used to dress seed of two new cotton varieties to control cotton diseases. | Demonstration trial planted at NaSARRI (Serere) but not at Lira and Kamuli districts. | 2000 | 1000 | CDO supported land preparation and planting of demonstration at NaSARRI, off-station work was not done. Dry spell affected the trial at NaSARRI | Data on seedling diseases collected and demonstrated the use of seeddressing chemicals in control of cotton wilts disease to afew farmers at NaSARRI in Serere | 2000 | At NaSARRI, seedling diseases recorded were alternaria, bacterial blight and wilt. Both BPAA 2015A (0.0%) andBPA 2015B (0.2%) showed better resistance to wilt compared to BPA 2002 (1.2%). Apron Star (0.0%) was more effective on wilt than Maxim (0.4%), Bronpal (0.4%) and CRuiser (1.2%). Bronopal (3.3%) was the most effective on bacterial blight compared to Maxim (5.0%) and Cruiser Extra (6.25%). | New pre-released varieties (BPA 2015A and BPA 2015B) had better resistance to wilt compared to BPA 2002. On seed dressing chemicals, Apron Star and Maxim were more effective to wilt while Bronopal was effective on bacterial blight. Demonstrations were not established in Lira and Kamuli |  | CDO supplimentary budget and payments are done directly to the labourers' phone numbers from CDO Head Office | Final data at NaSARRI collected and analysed. Popularize the most effective seeddressing chemical against cotton disease to afew farmers at NaSARRI in Serere | 2500 | The number of bolls was poor, for each plant had 0 to 3 bolls, so the seed cotton yields were not realised in this trial. | The late planting severely affected the trial and was worsened by drought and wild fire which destroyed all of replicate one. The 0 to 3 bolls did not show any seed cotton yield differences at NaSARRI. | 2000 | CDO suppported the maintenance (weeding and spraying) of the trial at NaSARRI | Data organized and reported on the most effective seeddressing chemical and levels of control of cottn wilts disease | 1500
| Off budget grants (HOPE 2 Project) |  |  | Activity 1.3. Keeping the breeding pipeline full | Output 1.3.1: Advanced populations with multiple traits identified for sources of resistance to biotic stresses (striga, midge smuts, and drought, blast) available annually | 1.3.1.2: Evaluating 25 sorghum lines for tolerance to striga in 2 sites (Namutumba and NaSARRI) | 70656 | Three striga resistant lines identified last season | Three striga resistant lines identified |  |  | Test the lines along with 10 advanced generation breeding lines derived from Framida,N13,104GRD and SEREDO | Two lines; IESV24029SH and 104GRD advnced to Multilocational testing for striga resistance in striga hot spots |  | One line recommended for adancement to NPT1 | AnewAset of fourteen lines have been composed for testing at NPT1 |  |  | Aset of fourteen lines have been composed for testing at NPT1 |  | Establish a trial s for NPT 1 at at 12 sites the onset of 1st rains | Selection of 13 sites for establishing NPT1 for striga with fourteen entries each.has been done for multilocational testing
[6 empty] | 1.3.1.3: Evaluating 16 sorghum lines for short duration adaptability in 2 sites (Karamoja and Kitgum) |  | At l east Four early maturing with good agromic attributes identified | Six lines identified for earlines (the ASARECA series) |  |  | Detailed morphological data correelated to drought responce need to be taken | Data on sttay green tait , grain filling has been taken to get insights of important traits that might influence crop productivity under stress and can contribute toward selection and development of drought varieties, |  | Overall picture of performance of genotypes at different locations determined | Overall picture of performance of genotypes at different locations validated |  | Trial was not planted in karamonja because of prolonged droughtProlonged drought | Aset of eight lines have been composed for testing in karamoja agro-ecology for adaptation and participatory selection |  | Establish th trial s onset of 1st rains in 3 sites in karamoja | Three sites have been selecteda , prepared land ready for planting to revalidate the results.
[6 empty] | 1.3.1.4: Evaluating 28 sorghum lines for smut resistance in one site at NaSARRI |  | Two lines with resistance to smuts identified | Two lines with resistance to smuts identified |  |  | These two lines have been incorporated in Advanced yield trials to be planted this season | One stable line SSEA35-2-2016S1 advanced to multilocational testing. |  | The elite line SSEA35-2-2016S1 advanced to NPT1 | Seed increases for elite line SSEA35-2-2016S1 for advancement to NPT1 |  | Prolonged drought affected grain yields from seed increase nurseries | Plant seed increase nurseries for adaptation trials |  | Breeder seed and maintenance | Line has been included in field experiments onstation during first rains to test for adaptation
[6 empty] | 1.3.1.5: Evaluating 25 sorghum hybrids for adaptability in 3 sites (NaSARRI, Ikulwe and NabuinZARDI-Karamoja) |  | Six hybrids with good nicking and higher yield than commercial OPV check NAROSORGH 1 were identified | Seven best performing hybrids were; ATX623 X MACIA, ICSA15 X ICSR160, ICSA15 X ICSA90001x ICSR172, ICSA90001 x ICSR160, ICSA1104 X ICSR8908 |  |  | Testing pollen production in isolations | Testing pollen production in isolations |  | Preliminary evaluation for pollen production identified ATX623 X SESO3 as best hybrids | One best hybrid identified |  | New hybrid was not produced becausece of the season. The parental lines got destroyed by weevils |  |  | Test for pollenproduction during favourable weather under isolations next season | Test for pollenproduction under isolations next season and adaptation to wider agro-ecology.
[6 empty] | 1.3.1.6: Evaluating 25 sorghum lines for sub-humid adaptability in 2 sites (Kamenyamiggo-Masaka and Mbarara) |  | Lines with high yield of 2500kg/ha comparable the NARO SORGH2 identifed from serere. in other sorghum growing agro-ecologies | Five lines with high yield of 2500kg/ha comparable the NARO SORGH2 identifed from serere. There adaptability needs to be ascertained in other sorghum growing agro-ecologies |  |  | There adaptability needs to be ascertained | Performance of lines for adaptation to subhumid altitudes validated for responses to biotic stress such as grain molds,root and stalk rot,downy mildew and anthracnose |  | Trial was not planted | Maintenance and seed increases continued |  | Maintenance and seed increase | Maintenance and seed increase of 10 advanced generation breeding lines/elite material |  | Maintenance and seed increase | Maintenance and seed increase nursey established
[6 empty] | 1.3.1.7: Evaluating 150 F5 sorghum smut resistant populations on station |  | Families with supeior agromic attributes identified | Four familes identified from early generattion teseting out thirty to to advanced to Preliminary yield trials |  |  | Preliminary yield trial to be planted .And further reselection for residual variability to be done | Derive lines with good grain yields |  | Two breeding lines identified from crosses were;SSEA35-2-1/2016S1 and SSEA52-1-2-2016S1 as top yielding with characteristic midseason drought stress pattern 30 dry days bewween the spells of rain |  |  | Advance to multilocational trials and maitennance | Multilocational trial established with 14 entries |  | Trial was so gappy following poor germination to the dry spell. | Multilocational trial established with 14 entries reconstituted for evaluation of stable smut disesaese resistance.
[5 empty] | Output 1.3.2: New populations drawing on known and newly identified sources of resistance to biotic stresses (striga, s.midge, and covered smut) to biotic stresses (drought) and preferred end user qualities produced annually | 1.3.2.1: Generating F1 populations for sorghum smut, midge, striga resistant populations on station |  | crosses tmade advanced to F1 in order to introduce variability for resistances | Ten crosses made |  |  | More crosses to be made | F1 Crosses were advanced |  | Strategic crossing among parents that encompass as many target traits as possible | 36 crosses made |  | Prolonged drought affected successful crossing | 26 crosses made |  | Prolonged drought affected successful crossing | Advance crosses and select F2 plants using the pedigree approach and measure rate of genetic gains in resistance to insect resistance(shoot fly,stemborer)
[5 empty] | a). To screen sorghum lines for sorghum midge resistance. | a) Sorghum germplasm identified to be furthersreened for resistance against the sorghum midge. | 12000 | a). To screen 12 promising sorghum lines identified for resistance against sorghum midge. | a)An experiment to screen 12 sorghum genotypes for resistance against sorghum midge ; (IESV25009SH, SEREDO, WAGITA, IESV25025SH, IS 8193, IESV25012SH, IESV25027SH, IESV25007SH, IESV25010SH, NAKHADABO, IESV25011SH, and IESV25001SH) was set up but heavily attacked by the fall army worm and the crop failed to perfom well during 2018A. | 2000 |  | To repeat the screening experiment during season 2018B. | Land preparation and seed secured awaiting the seasons rains 2018B to plant. | 3000
[5 empty] | Output 1.3.3: New hybrid parents (5) derived from local germplasm with tolerance to drought and resistance to striga identified annually | 1.3.3.1: Evaluating 15 sorghum hybrid parent (A and B) lines for combining ability and fertility restoration |  | Three best combiners with NAROSORGH1,IESV92172DL and ICSR 89058 under F1 test cross evaluation. |  |  |  | 1st Backrossing to done to develop A and B parental lines |  |  | The backcrossing could not be countinued because the male parents are only suitable for hybrid making since the showed full fertility restoration at F1. |  |  | Use a pool of genotypes from different breeding projects in Test cross evaluation | We evaluated new set of 18 A& B pairs against 51 porential restores and generated Test crosses for evaluation |  | 40 Test crosses made | 40 Test crosses made for evaluation next quarte for combining ability and restoration |  | Four A- lines are unstable for sterility locus i.e ICSA 1104,ICSA11034,ICSA 654.ICSA88006.This perhaps due to enviromentantal interaction
[5 empty] | 1.2.1.4 Screening all available finger millet germplasm under glasshouse conditions for their response to drought at seedling stage and selecting top performing 200 for subsequent field screening | Drought tolerant germplasm for finger millet identified |  | Materials for setting up experiment is under procurement
[5 empty] | 1.2.1.5 Screening a diverse set of finger millet germplasm under glasshouse conditions for their response to Striga | striga tolerant germplasm for finger millet identified |  | Materials for setting up experiment is under procurement
[5 empty] | 1.3.1.8 Evaluating 180 finger millet lines for drought tolerance and grain yield | drought tolerant germplasm for finger millet identified |  | 1 acre of land was prepared | land prepared ready for trial establshment |  |  |  | land prepared ready for trial establshment |  | drough tolerant breeding trial established | trial was planted, weeded, thined and data collected |  |  |  |  | 23 best perfoming drought tolerant lines selected | trial harvested, data analysed and 23 best performing lines selected for futher evaluation
[5 empty] | 1.3.1.8 Evaluating 25 finger millet lines for blast resistance, drought and striga tolerance and grain yield | 15 finger millet lines advancet to NPT |  | harvesting of trials were done
[5 empty] | 1.3.13.1: Evaluating 81 finger millet lines for blast resistance on-station and atleast 10 best performing lines (balst, striga, nutreints) advanced to MLT. | 10 best performing lines advancet to ADYT |  | Harvesting of trials were done
[5 empty] | 1.4.5.3 Evaluating 16 lines at NPT/ DUS for drought, Blast and striga for possible release in 2019 | data entry is on going |  | not done
|  |  | Unraveling the molecular genetics of finger millet blast disease and the existing resistance for the development of high-yielding resilient varieties | Generation of agricultural technologies | 2.1.2.1 Enhancing NaSARRI to produce breeder seeds | 350 kg of improved finger millet varieties produced |  | land preparation was done | land prepaared ready for seed multiplication | 960 |  |  |  |  | finger millet breeder seed multiplie | seed multiplication field established and maintained |  | five new variety of finger millet seed is under field multiplication | four acres of breeder seed established, weeded, thined and well maintained |  | Breeder seed harvested | breeder seed hrvested, dried and threshed |  |  | Ten finger millet seedlings established, inoculated with 12 M. oryzae isolates, data recorded and analysed | 5000
|  |  |  | Generation of agricultural technologies | Infection of a panel of 10 finger millet differentials with 26 selected monoconidial Magnaporthe oryzae isolates | Two aggressive isolates from any four countries identified | 20000 | 26 monoconidial M. oryzae isolates multiplied in laboratory, seedlings of 10 finger millet plants established and inoculated in the screen house | Monocondial isolates not multiplied, for isolates are kept in Pwani Universty, Kenya | 5000 | 0 | Isolates are kept in Kenya due to lack of cold (-20 C) facilities at NaSARRI. Need to transfer the isolates to NaSARRI but currently there are no project funds. | 25 monoconidial M. oryzae isolates multiplied in laboratory | 5000 |  |  |  |  | Ten finger millet seedlings established, inoculated with 14 M. oryzae isolates, data recorded and analysed | 5000 |  |  |  |  | Finger millet seedlings of 30 lines established and inoculated in the screen house, data summarised and analysed | 4000
|  |  |  | Generation of agricultural technologies | Phenotype of 120 accessions with two blast isolates | Ten finger millet blast resistant lines identified | 10000 | Finger millet seedlings of 30 lines established, inoculated in the screen house and data collected | Not done | 3000 | 0 | This awaits the identification of 2 M. oryzae isolates | Finger millet seedlings of 30 lines established, inoculated in the screen house and data collected | 3000 |  |  |  |  | Finger millet seedlings of 30 lines established, inoculated in the screen house and data collected | 4000 |  |  |  |  | Data on blast and grain yield data recorded in Pallisa, Kumi, Amolatar, Lira and Kitgum summarised and analysed | 3000
[5 empty] | Identification of high yielding, blast resistant finger millet accessions | Ten finger millet high yield blast resistant lines identified | 10000 | 25 finger millet lines planted in Pallisa, Kumi, Amolatar, Lira and Kitgum | Data on finger millet blast recorded in Pallisa, Amolatar, Lira and Kitgum | 4000 | 0 | The trial in Muntu was left to bush | Data on blast and grain yield data recorded in Pallisa, Kumi, Amolatar, Lira and Kitgum summarised and analysed | 3000 |  |  |  |  | 16 finger millet lines selected for good resistance to blast and yield planted in Pallisa, Kumi, Amolatar, Lira and Kitgum | 4000
[5 empty] | 2.1.3.1 Developing and validating one module/protocol for the production/ maintenance of breeders’ seed | 1 production guide developed |  | draft manual ready for review
| Off budget grants (ITPGRFA - EU: CGS Project) |  |  |  | Activity 1.3: Germplasm evaluation and conservation |  | 11467.5 | a) Germplasm for 6 project crop commodities characterised for field perfomance. | Land preparation ready for establishing the germplasm characterisation durinh 2018B | 4000 |  | Funds were not available in time to carry out the activity during 2018A. | Preparing to carry out germplasm charecterisation during season 2018B | 4000 | Due to prolonged drought, the trial for germplasm characterisation was not planted. Deferred to season 2019A. | Project germplasm to be characterised. |  | The trial to be conducted at the onset of season 2019A rains. | Securing land for germplam evaaluations and characterisation. | 2000 | Land secured ready for use 2019A season. | Land secured ready for use in germplasm evaluation during 2019A season. |  | Waiting for the 2019A rainy season.
[5 empty] | Activity 2.1.1: Establishing the seed delivery model - Farmer group mobilization and training | Effective and sustainable seed delivery model established to increase access to quality seed | 17330.111 | 462 farmers (232 females: 230 males) from 30 groups mobilised and trained in proper agronomic practices using demo gardens during 2018A. | A cumulative total of 1,069 farmers (552 males : 517 Females) from 30 groups in the 3 project districts trained in proper agronomic practices, during 2017A & 2018A. | 5000 |  | Funds were disbursed late to implement activities | a). A). Farmers to be trained in quality seed production, post harvest management, Safe use and handling of pesticides, stores management and Book keeping. b). Crop production guides to be translated into Luo and Ateso local languages. | 6000 | 60 ToT Farmers (Males 40: Female 20) were trained in post harvest handling, safe use and handling of pesticides, record and book keeping, and Quality seed production, in the project areas | A cumulative total of 1,129 Farmers (Males 592 : Females 537) were trained in good agronomic practices of quality seed production. |  | To follow up encouraging famers how to keep records and financial books of their seed granaries once the granaries are constructed. | Followup and ensure farmers perfect quality seed production, conservation, and shared amongst others who are interested. | 2000 | To organise farmer field days and exchange vists to sharing information as well as learning events. | Enable information sharing amongst the farming communities. |  | Waiting for the rainy season and better crops for showcasing the farmer's effeort in producing quality seed, crop commodity diversity as well as their conservation.
[5 empty] | Activity 2.1.2: Establishing the seed delivery model - Implementation | Effective and sustainable seed delivery model established to increase access to quality seed | 10749.4 | a). 18 Sites identified and ready for granary construction . b). Land for granary construction secured and MoUs signed with the local Governmnent. authorities. C). Farmers given initial seed to start multiplication in their respective groups. Seed multiplication for both improved and desired local seed varieties for six (6) project crop commodities (sorghum, finger millet, pearl millet, cowpea, pigeon peas and groundnuts) by farmers ongoing. | a). Farmers mobilsed into 30 groups b). 18 Sites for granary construction identified, assessed and MoUs signed with the respective Local Government Authorities. c. Adjustment of the seed store building plans finalised with and awaiting tendering out for bidders to commence construction in all the sites adentified. d). Seed multiplication for both improved and desired local seed varieties for six (6) project crop commodities (sorghum, finger millet, pearl millet, cowpea, pigeon peas and groundnuts) by farmers. | 10000 |  | Late disbursement of project funds affected planning and timely implementation. | Seed granaries |  | 600 Farmers given initial seed to start multiplication in their respective groups. A total of 333 individual farmers were added Seed for multiplication. Individual households and 30 farmer groups engaged in quality seed multiplication. b). The seed granaries have not yet been constructed by FAO Uganda. | 600 Farmers given initial seed to start multiplication in their respective groups. A total of 333 individual farmers were added Seed for multiplication. Individual households and 30 farmer groups engaged in quality seed multiplication. b). The seed granaries have not yet been constructed by FAO Uganda. |  | Individual households to be given seed to multiply during seeason 2019A. FAO Uganda to call for bids to construct the community seed granaries. | a) Land for granary construction secured. b). Architectural plans and Bills of Quantities ready, and awaiting tendering for contractors to commence the seed granaries construction. c). Farmer groups to be given another set of initial seed (other commodities) to continue with quality seed multiplication come season 2019A. | 15000 | a) Land for granary construction secured. b). Architectural plans and Bills of Quantities ready, and awaiting tendering for contractors to commence the seed granaries construction. c). To secure initial seed to be given to farmer groups for multiplication, come season 2019A. | a) Land for granary construction secured. b). Architectural plans and Bills of Quantities ready, and awaiting tendering for contractors to commence the seed granaries construction. c). To secure initial seed to be given to farmer groups for multiplication, come season 2019A. |  | a). Waiting for contractors to commence granary construction b). Waiting for funds to procure initial seed for farmer groups, 2019A.
[5 empty] | Activity 3.7: Follow up project activities in field | Monitor implementation of project activities in field | 9900 | a). Monitoring of project activities conducted during the reporting period. | a). Monitoring of project activities continued. | 3000 |  | Monitoring of project implementation done by CGS project and NARO staff | a). Monitoring of project activities conducted during the reporting period. | 3000 | a). Monitoring of project activities carried out by CGS Project and WVU staff, FAO Representative. | a). Monitoring of project activities carried out by CGS Project and WVU staff, FAO Representative. |  | To conduct a project monitoring and Evaluation exercise once funds are available during season 2019A | a). Monitoring of project activities conducted during the reporting period. | 3000 | a). Monitoring of project activities continued.
[7 empty] | 26829 | a). Procure key stationery supplies for use. | a). Key supplies procured for use in project implementation. | 1500 |  |  | a). Acquire materials and equipment for running the project | 1500 | a). Procured stationery for project implementation, b). Received agricultural iput supplies (pesticides, pesticde application protective ware) and other inputs from the ITPGRFA - Italy | a). Procured stationery for project implementation, b). Received agricultural input supplies (pesticides, pesticde application protective ware) and other inputs from the ITPGRFA - Italy. Not all inputs promised have been delivered to Uganda. |  | Expecting the remaining agro inputs from the ITPGRFA, Italy. | Distributed the agroinputs received to farmers to use for safety purposes. | 2000 | a). Seed harvested by farmers was conserved ready for the rainy season 2019A. b). Farmers identified land for seed multiplication come the rainy season, 2019A. | a). Seed harvested by farmers was conserved ready for the rainy season 2019A. b). Farmers identified land for seed multiplication come the rainy season, 2019A. |  | Farmers to share the seed and as well as conserve some for futeure use in the seed granaries to be constructed.
[5 empty] | Activity 4.5: Project planning and review meetings |  | 1320 | a). Hold regular Project planning and Review meetings. | a) Held 1 project planning and 1 Review meetings during the period | 500 |  |  | a). Held 2 Project planning and review meetings with the CGS technical team (scientists) at NaSARRI and World Vision Uganda head office. | 5,00 | a) Held 1 project planning and 1 Review meetings during the period | a). Held 1 Project planning and review meeting with the CGS technical team (scientists) and WVU team at NaSARRI. 2018 |  |  | To hold a pre-season project planning meeting with partners WVU, and project staff 2019A. | 2000 | To hold a pre-season project planning meeting with partners WVU, and project staff 2019A. | To hold a pre-season project planning meeting with partners WVU, and project staff 2019A.
[5 empty] | Activity 4.6: Project Monitoring and evaluation. | Project Monitoring and evaluation conducted. | 3000 | Project monitoring and evaluation was not conducted due to delayed disbursement of funds. | Hold regular project implementation meetings. | 5000 |  |  | a) To conduct a project monitoring and evaluation exercise, during 2018B. | 2000 | Hold regular project implementation meetings. | a). No project minitoring and evaluation exercise has been held as yet. |  | To conduct an M&E exercise immediately thye funds are received. | To hold consultative meetings with WVU officials, as well as the FAO Uganda representative on seed production and conservation. | 3000 | To hold consultative meetings with WVU officials, as well as the FAO Uganda representative on seed production and conservation. | To hold consultative meetings with WVU officials, as well as the FAO Uganda representative on seed production and conservation.
[5 empty] | Activity 5.0: Visibility plan (Brochures, Banners, eardrops pull ups etc) | Visibility materials developed and distributed/ used (Brochures, Banners, eardrops pull ups etc) | 3649.8 | a). Brochure about the project developed and used for project visibility. b). Brochures on on production guides translated in to local languages for use by farmers, c). Other visibility materials used included invitation letters, project over view presentatations, NaSARRI website and sign posts at demo gardens during 2018A. | 600 copies of training quality seed production brochures were produced and given to the farmers during training 2018A. Translation into local languages ongoing. | 2000 |  |  | a) Establish visibility materials including CGS Project brochures, invitation letters, project over view presentatations, NaSARRI website and sign posts developed and used. | 1650 | a). 300 copies of crop productions notes produced and used in training farmers in post harvest handling, record and book keeping, safe use and handling of pesticides, and quality seed production. b). Printed a CGS Project banner and Pull-up for visibility. c). Participated in the World Food Day Exhibitions in Moroto. d). Participateed in the UN Day exhibition in Kololo Kampala. | a). 300 copies of crop productions notes produced and used in training farmers in post harvest handling, record and book keeping, safe use and handling of pesticides, and quality seed production. b). Printed a CGS Project banner and Pull-up for visibility. c). Participated in the World Food Day Exhibitions in Moroto. d). Participateed in the UN Day exhibition in Kololo Kampala. |  | a). Translation of crop production guides into local languages of Ateso and Luo is on-going. | a). Translation of crop production guides into local languages of Ateso and Luo is on-going. | 2000 | Two Project scientists are translating the crop production guides into Luo and Ateso local languages. | Crop production guides for finger millet, sorghum and pearl millet were translated into Ateso, and are ready for printing copies for circulation and use by farmers once the funds are availed. |  | Awaiting completion of translation of the crop production guides into Luo local language.
| Off budget grants (IBP/IFAD Project) |  | Enhancing institutional breeding capacity in Ghana, Senegal and Uganda to develop climate resilient crops for African smallholder farmers | Generation of agricultural technologies | Evaluate pre-released cowpea lines in national performance trials (NPTs) | High yielding and widely adaptable genotypes identified. Location/niche specific genotypes identified. | 15000 | [5 empty] | Design mother trials. Establish mother trials for 25 pre-released cowpea lines in 4 locations. Design data collection tools/template. Collect disease, agronomic and yield data | 6000 | Mother trials for 27 advanced lines + 3 checks designed for 4 locations. Trials were planted at NaSARRI, AbiZARDI, NgettaZARDI, and Kitgum satellite station. Agronomic and disease data (viral, scab, powderly mildew and bacterial blight) collected | Mother trials for 27 advanced lines + 3 checks designed for 4 locations. Trials were planted at NaSARRI, AbiZARDI, NgettaZARDI, and Kitgum satellite station. Agronomic and disease data (viral, scab, powderly mildew and bacterial blight) collected | 6000 |  | Data entry and preliminary analysis. Generated new experimental designs, prepare land (ploughing), prepare/pack seed for 2019 first season planting. | 3000 | mother Trials for 27 lines +3 checks planted at 4 locations were harvested, samples threshed, post harvest data collected and entered. Samples were dressed. Land preperation is 2019A season started | Mother trials for 27 advanced lines + 3 checks planted in 4 locations (NaSARRI, AbiZARDI, NgettaZARDI, and Kitgum satellite station) were harvested, Agronomic and disease collected and entered. Land preparation for 2019A started | 3000 | There has been delay in land preparation/planting due to late rains | Establish mother trials for 25 pre-released cowpea lines in 4 locations. Collect disease and agronomic data | 6000
[5 empty] | Document farmer preferances (selection criteria) for improved cowpea genotypes | Farmers’ feedback on trait preferences and new germplasm characteristics available in the knowledge platform | 6000 | [17 empty] | Capture farmers’ feedback on cowpea trait preferences | 6000
[5 empty] | Monitor and implement BMS use in the institute | BMS used routinely by 5 to 10 breeders/technicians in the institute | 2000 | [5 empty] | BMS focal persons identified for the institute and trained by IBP, and BMS deployment activities monitored. | 750 | Two project staff in the legumes program trained on the use of BMS by IBP regional support team | Two project staff in the legumes program trained on the use of BMS by IBP regional support team | 700 |  | BMS focal persons identified for the institute and trained by IBP, and BMS deployment activities monitored. | 750 | 2 program Staff have been trained | 2 program Staff (tecnician and field asssitant)were trained | 700 |  | BMS focal persons identified for the institute and trained by IBP, and BMS deployment activities monitored. |  |  | 500
[5 empty] | Screening of MAGIC population (200 lines) and minicore lines (300 lines) for heat and drought tolerance | Heat and drought tolerant MAGIC and mini-core lines identified for use by breeders and /or cultivation by farmers | 8000 | [5 empty] | Generate experimental designs, land preparation, plant trials, carry out weeding, thinning, pest and disease management, collect data and harvest trials | 3000 | Trials not planted | Trials not planted |  | Insufficient seed quantities | Drying and threshing of harvested trials. Yield data measurement. Data entry and preliminary analysis | 2000 | First trial planned for 4 quarter. Land preparation is ongoing | First trial planned for 4 quarter. Land preparation is ongoing | 1000 | Late rains | Generate experimental designs, plant trials, carry out weeding, thinning, pest and disease management, collect data and harvest trials | 3000
[5 empty] | Genotyping of pre-released promising cowpea lines | Genetic relationships among pre-released lines established | 5000 | [17 empty] | Carryout DNA Fingerprinting of 25 pre-released cowpea lines | 5000
[5 empty] | Phenotyping of pre-released promising lines | Phenotypic relationships among pre-released lines established | 6000 | [11 empty] | Generate experimental designs. Prepare land for field trials. Prepare and pack seed for pre-released lines | 2500 | Seed has been prepared and packed. Land preparation started | Seed has been prepared and packed. Land preparation started | 1500 | Late rains | Establish trials for phenotyping pre-released lines. Collect data. | 3500
|  |  |  | Research extension interface promoted and strengthened | Training of youths in quality cowpea seed production | Capacity to produce sufficient quality seed strengthened | 6500 | [11 empty] | Identification and selection of youthful farmers (50 farmers). Design of training materials/curriculum | 2500 | Not done | Not done |  | Activity will be considered for the in quarter 4 | Conduct training of youth farmers in cowpea seed production | 4000
[5 empty] | Production of breeder/foundation seeds for new varieties and distribution to farmer groups and other stakeholders | Sufficient quantities of early generation seed available to uptake pathways | 5500 | [5 empty] | Land preparation and planting of cowpea foundation seed multiplication fields 2 acres for 3 varieties. Weeding, thinning, pest and disease management of seed production fields. Roguing and harvesting | 2200 | 3.5 acres of land prepared for production of breeder amd foundation seed on station. Seed of three varieties planted on station (SECOW3B, NAROCOWPEA5 and SECOW2W). Weeding, thinning, pest control and roguing carried. | 3.5 acres of land prepared for production of breeder amd foundation seed on station. Seed of three varieties planted on station (SECOW3B, NAROCOWPEA5 and SECOW2W). Weeding, thinning, pest control and roguing carried. | 2200 |  | Drying, threshing and sorting of harvested cowpea seed. Land preparation for another round of seed multiplication/bulking | 1000 | Drying, threshing and sorted of breed for SECOW 3B, SECOW2W, NAROCOWPEA 5 done. Land preparation for 2019A started | Drying, threshing and sorted of breed for SECOW 3B, SECOW2W, NAROCOWPEA 5 done. 400 kg of breeder seed produced for SECOW 3B, 50kg for SECOW2W, 100kg for NAROCOWPEA 5 | 1000 |  | Planting of seed multiplication fields, Weeding, thinning, pest and disease management of seed production fields. Roguing and harvesting | 2300
| Off budget grants (WorldVeg/AVRDC Project) |  | Triggering a mungbean transformation in Africa | Generation of agricultural technologies | Characterization of mungbean mini-core collection | Potential sources of resistance/tolerance to major mungbean biotic and abiotic stresses identified | 15000 | [5 empty] | Apply for seed import permits, obtain seed from WorldVeg, site selection and land preparation, generate designs, sowing, weeding, data collection, harvesting, drying, threshing, data entry | 9000 | Import permit for 293 mungbean mini-core collection (MMC) accessions obtained from MAAIF. Seed for MMC obtained from Worldveg. Trials were planted at NaSARRI. Insect traps (blue and yellow sticky traps) installed. Disease and pest data collected. Trials harvested | Import permit for 293 mungbean mini-core collection (MMC) accessions obtained from MAAIF. Seed for MMC obtained from Worldveg. Trials were planted at NaSARRI. Insect traps (blue and yellow sticky traps) installed. Disease and pest data collected. Trials harvested | 9000 |  | Site selection, land preparation, generation of designs, seed sorting and packing | 1500 | Experimental trial site was selected, land preparation started, designs have been generated for 2019A. Seed had been packed and dressed. | 293 mungbean mini-core collection (MMC) accessions were obtained from Worldveg. Disease and pest data collected. Trial design for 2019A season generated | 1500 |  | sowing, weeding, data collection, harvesting, drying, threshing, data entry | 10000
[5 empty] | Multi-location evaluation of High potential mungbean lines in variety trials | Adapted, high potential lines identified for further testing in farmer fields under rainfed and irrigated conditions | 20000 | [5 empty] | Apply for seed import permits, obtain seed from WorldVeg, site selection and land preparation, generate designs, sowing, weeding, data collection, harvesting, drying, threshing, data entry | 8000 | Import permit for 54 mungbean breeding lines (BL) obtained from MAAIF. Seed for BL obtained from Worldveg. Trials were planted at NaSARRI, AbiZARDI, Kitgum satellite station and NgettaZARDI. Insect traps (blue and yellow sticky traps) installed. Harvesting partially done (at NaSARRI and Kitgum satellite station) | Import permits for 54 mungbean breeding lines (BL) obtained from MAAIF. Seed for BL obtained from Worldveg. Trials were planted at NaSARRI, AbiZARDI, Kitgum satellite station and NgettaZARDI. Insect traps (blue and yellow sticky traps) installed. Disease and pest data collected. Harvesting partially done (at NaSARRI and Kitgum satellite station) | 8000 |  | Site selection, land preparation, generation of designs, seed sorting and packing | 2000 | Experimental trial site was selected, land preparation started, designs have been generated for 2019A. Seed had been packed and dressed. | 54 mungbean breeding lines (BL) were obtained from Worldveg. Trials were planted at NaSARRI, AbiZARDI, Kitgum satellite station and NgettaZARDI. Disease and pest data collected. Harvesting completed. Experimental trial site was selected, land preparation started, designs have been generated for 2019A. Seed had been packed and dressed. | 2000 |  | sowing, weeding, data collection, harvesting, drying, threshing, data entry | 10000
|  |  |  | Research extension interface promoted and strengthened | Scaling-training of farmers and extension workers in mungbean production practices | Capacity of farmers and extension staff in mungbean production enhanced | 16000 | [11 empty] | Selection of sites, identification of farmers/groups and extension workers | 6000 | Selection of sites and identification of farmers/groups and extension workers done in Budaka, Palisa, Katakwi and Kaberamaido districts | Selection of sites and identification of farmers/groups and extension workers done in Budaka, Palisa, Katakwi and Kaberamaido districts | 6000 |  | Training of farmers and extension staff | 10000
[5 empty] | Scaling- Farmer promotion of GAPs | Good mungbean agronomic practices promoted for uptake | 18000 | [11 empty] | Selection of sites, identification of farmers/groups | 6000 | Selection of sites and identification of farmers/groups and extension workers done in Budaka, Palisa, Katakwi and Kaberamaido districts | Selection of sites and identification of farmers/groups and extension workers done in Budaka, Palisa, Katakwi and Kaberamaido districts | 6000 |  | Establishment of demonstration plots, weeding, pest and disease management, data collection | 12000
[5 empty] | Production of breeder/foundation seeds for new varieties and distribution to farmer groups and other stakeholders | Sufficient quantities of early generation seed available to uptake pathways | 20000 | [5 empty] | Land preparation and planting of mungbean foundation seed multiplication fields 2 acres for 3 varieties. Weeding, thinning, pest and disease management of seed production fields. Roguing and harvesting | 7000 | 2.5 acres of land prepared for planting of mungbean breeder and foundation seed (NAROGRAM1 and NAROGRAM2). Planting was done. Weeding, thinning and pest management carried out. | 2.5 acres of land prepared for planting of mungbean breeder and foundation seed (NAROGRAM1 and NAROGRAM2). Planting was done. Weeding, thinning and pest management carried out. | 7000 |  | Drying, threshing and sorting of harvested mungbean seed. Land preparation for another round of seed multiplication/bulking | 3000 | Drying, threshing and sorting of harvested mungbean seed. Land preparation for 2019A started | 2.5 acres of land prepared for planting of mungbean breeder and foundation seed (NAROGRAM1 and NAROGRAM2). Drying, threshing and sorting of harvested mungbean seed. Land preparation for 2019A started | 3000 |  | Planting of seed multiplication fields, Weeding, thinning, pest and disease management of seed production fields. Roguing and harvesting | 10000
[5 empty] | Scaling- Establishment of seed villages for scaling | Farming communities access to improved mungbean seed enhanced | 35000 | [11 empty] | Selection of sites, identification of farmers/groups, avail foundation seed to farmers, | 15000 | 3 Local seed business groups in Nebbi (Wadelai), Lira (Amach), Kole identified for seed multiplication and marketing | 3 Local seed business groups in Nebbi (Wadelai), Lira (Amach), Kole identified for seed multiplication and marketing | 1500 |  | planting, weeding, pest management, harvesting | 20000
[5 empty] | Rapid mungbean value chain development | Well developed mungbean market | 15000 | [5 empty] | Develop protocols for carrying out value chain analysis study | 5000 | NOT done | Not done |  | Activity pushed to 3rd quarter | Conduct value chain study | 10000 | Protocol developed | Protocol developed
| Off budget grants (Sorghum-Lugeme CCRP Project) | Dryland cereals/Oil crops Program | Enhancing food and nutritional security using sorghum-legume interventions for improved livelihood among smallholder farmers in Uganda | Generation of agricultural technologies | Participatory rural appraisal to understand smallholder farmers’ knowledge, constraints and practices related to soil health and management | Farmers’ knowledge, constraints and practices related to soil health and management identified and documented | 22000 |  | A reconnaissance study was conducted and we identified that farmers use cowpeas, beans, greengram, and groundnuts for both intercrop/rotation |  | 21500
[5 empty] | Multi-locational trials and participatory sorghum variety Selection | Two sorghum lines with good quality attributes identified and selected together with the farmers | 13000 | Seed sorting and site identification for multi-locational trials | Sites were identified in Bukedea and Apac. Land preparation has also been done and the field will be planted as soon as rains come |  | 4000 | The long dry spell has affected timely implementation of planned activities | Establishement of PVS trials in different sites previously identified | 4000 | Establishement of PVS trials in different sites previously identified | Establishement of PVS trials in different sites previously identified | 4000 |  | Field day held to select/identify the best perfoming sorghum vaieties by the farmers and resaerchers | 5000 | Inter |  |  |  | sorghum variteis with good quality attributes identified and applied for release. | 2000
[5 empty] | On-farm testing and demonstrations of sorghum-legume cropping system (intercropping and crop rotation) | Most prefered and efficient sorghum legume cropping system in soil health management identified | 12000 | Identify the most preferd legumes used in a sorghum cropping system and how these are integrated in the cropping system | A reconnaissance study was conducted and we identified that farmers use cowpeas, beans, greengram, and groundnuts for both intercrop/rotation |  | 3000 | [9 empty] | Repeat the soil health trials in Amuria, Bukedea, Soroti and PalLisa and NaSARRI -serere districts. With 11 farmers per site giving a total of 44 farmers to test the treatments of (1) N microdoze, P-microdoze, FYM and combinations (2) intercroppping (broadcast, 2:1 and 2:2 patterns) and the (3)rotations of Gnut/ sorghum, sorghum/cowpea and sorghum/greengram) | Farm selection, field preparation were done and planting is on progress
[5 empty] | Germplasm collection, screening/ characterization and selections of sources of resistance to smut, stem borer, midge, striga, | Sources of resistance to smuts and stem borer identified | 12000 | Atleast 150 accessions collected and planted for generation of passport data | We collected 146 local germplasm from farmers in the eastern and northern regions and these are yet to be evaluated |  | 4000
[5 empty] | Intogression of smut and stem boror resistance traits into farmer preffered susaceptable genotypes | 5 F1 crosses maded | 7000 | Potential parental lines identified via screening of the accessions | Not yet achieved |  | 1200 | The prolonged dry spell has caused delays in establishment of the trials
|  |  |  | Research extension interface promoted and strengthened | Multiplication of improved seeds by researchers and farmers | Two tonnes of improved sorghum seed obtained and distributed to individual farmers and farmer groups |  | Seed increase (multiplication on station) of 3 improved sorghum varieties and identification of farmers for the subsquent multiplication. | Not achieved |  |  | The unpredictable weather patterns affected implentation of this activity as farmers were reluctant to take the risk of planting without stable rains | Distribution of the seeds obtained to individual farmers and farmer groups for planting | 4000 | Not archieved due to drought | Distribution of the seeds obtained to individual farmers and farmer groups for planting | 4000 |  | Monitoring and technical backstopping of farmers engaged in seed production | 5000 | Distributed and planted seed equivalent to 1.5 tones of Seso3, Narosorg2, N.56, and M.60 to farmer groups in Bukedea, Pallisa, Kibuku, Soroti and Amuria. However drought has already affected mosst of the fields | Distributed and planted seed equivalent to 1.5 tones of in five districts | 4000 |  | 2 tonnes of sorghum seed obtained for distibution to various uptake pathways. | 3000
[5 empty] | Capacity building (training of farmers, farmer groups, and seed merchants) on community seed system and marketing | Four demonstration plots established,1 field day and 3 farmer groups trainned and equiped with skills in production of quality declared seed |  | Training modules developed and identification of target farmers. | Three demo gardens and two field days were conducted in Soroti Katakwi and Bukedea |  | 3000 |  | One workshop to train farmers on sorghum agronomic practices held | 5000 | Training of three farmer groups (Awalwal,Damasco & Kagumu) on agromic practices of sorghum | Two farmer groups trainned | 5000 |  | Four demonstration plots estblished and field days conducted in the project area for practical learning | 3000 | Four farmer groups two in Soroti, one in Bukeda and One in Pallisa were trainned. Collectevilly over 200 farmers were trainned but within these groups, 20 farmers were identified and trainned farther as key trainners |  |  |  | One workshop to train farmers on postharvest handling of quality declared seed of sorghum held. | 4000
[5 empty] | Evaluation of different sorghum seed deliverly models | The most efficient and effective seed deliverly model identified |  | Identify the groups to work with during the project cycle | Eight farmer groups have been identified in Soroti, Pallisa, Bukedea, Kumi and Amuria |  | 3000 |  | One workshop to train farmers on sorghum agronomic practices held | 5000 | Training of three farmer groups (Awalwal,Damasco & Kagumu) on agronomic practices of sorghum | Three farmer groups trainned | 5000 |  | Four demonstration plots estblished and field days conducted in the project area | 3000 | Seed was distributed and multiplication field established for the two different models |  |  |  | One workshop to train farmers on postharvest handling of quality declared seed of sorghum held. | 4000
[5 empty] | Workshops and meeting | Mid year and annual reports completed | 9000 | Mid year review workshop |  |  |  |  | Annual project review and CCRP annual workshop | 9000 |  |  | 9000 |  |  |  | Not planned for the quarter
| Off budget grants (Vegetable Oil Development Project) VODP 11 | Oil crops Reseach Programme | Development of sunflower varieties with high oil content and quality; resistance to major diseases and pests; and appropriate crop management options | Research extension interface promoted and strengthened | Multiplication of breeder seed of new sunflower varieties | Breeder seed disseminated to uptake path ways for production of foundation seed | 4000 | Fields for breeder seed production ploughed and planting was done | Four acres planted with parental lines (A & B) lines plus the restorors in isolation | 1400 |  | The long dry spell affected timely establiment of the trials | Bird scaring, harvesting and seed cleaning of the breeder seed for foundation seed and evaluation of the constituted hybrids | 1200 | Four acres planted with parental lines (A & B) lines plus the restorors in isolation, however drought severly affected them. | Four acres planted with parental lines (A & B) lines plus the restorors in isolation | 4000 |  |  | 500 | About 200Kgs of seed were harvested and will be used in the multiplication |  | 0 |  |  | 900
|  |  | Development of sesame varieties with high oil content and quality with appropriate crop management options | Generation of agricultural technologies | Evaluate promising sesame lines for resistance to Cercospora and Cylindrosporium leafspots across locations | Sesame lines with resistance to Cercospora and Cylindrosporium leafspots identified | 9000 | Data sets on damage by Cercospora and Cylindrosporium leafspots on selected sesame lines at NaSARRI and TVCs recorded | Trials planted at 4 sites | 2500 | 0 |  | Yield data recorded on sesame genotypes for resistance to Cercospora and Cylindroporium leafspots at NaSARRI and TVCs | 2500 | Data on damege by cercospora and Cylindrosporium leafspots was collected at 4 different sites (Tororo, Kaberamaido, Ngetta and Kitgum TVCs). Harvesting is on going | Multi-locational trials established at four sites. Disease and yield data is being processed | 2000 |  |  | 1500 | twenty sesame genotypes were evaluated in six centres of Serere, Tororo, Kaberamaido, Ngetta, Kitgum and Abii (West Nile). Four lines (RENNER 1-3-1-17, (SESIM 2//5181)//2-2-1, (SESIM 2//5181)//7029-1-2-1 and AJIMO A1-6//7029-1-1) showed better resistance to disease compared to the control. These were | Four lines identified as possible sources of resitance to Cercospora and Cylindroporium leafspots+W164 |  |  |  | 2500
|  | Oil crops programme |  |  | Characterisation of the late and early leafspot pathogens | Effective management options for early leaf spot and leaf miner identified | 8000 | Diseased plant materials collected from different parts of the country for isolation and laboratory analysis | Twenty samples were collected within the Teso region and isolaton of the pathogen is on-going | 2000 | 1000 |  | Data sets from trial set up in quarter one recorded | 1626.3 |  | Survelience studies are yet to be conducted starting with the eastern and Northern regions | 1626 |  | Data sets from quarter two processed and analyzed & effect of chemicals and cultural practices on leaf spot and leaf miner damage validated | 1300 | Diseased plant tissues were collected in the northern and estern part of the country. Laboratory isolation and identification is on-going onstation | 92 Diseased plant tissues samples were collected for laboratory analysis |  |  |  | 1300
|  |  | Adaptive research on sunflower, sesame and groundnuts | Generation of agricultural technologies | Multilocational evaluation of advanced groundnuts lines, sesame and sunflower hybrids | One candidate variety each (groundnuts, sunflower and sesame submitted for DUS and eventual release | 55000 | Multilocational evaluation trials of at least 20 advanced lines planted | Multilocational Trials for (Sesame, Gnuts and Sunflower) were established in 16 different sites including the major TVCs in eastern and Northern Uganda | 25000 |  |  | Data set to identify the best performing lines collected and analyzed. Tens lines selected. | 10000 |  | Multilocational Trials for (Sesame, Gnuts and Sunflower) were established in 16 different sites including the major TVCs in eastern and Northern Uganda | 10000 |  | Ten lines planted during 1st rains for further selection of 5 what to submit for DUS | 10000 | Multi-locational trials for the three oil seed commodities established at different sites in the districts of Serere, Tororo, Kaberamaido, Ngetta, Kitgum, Pader, Abi, Kiryandongo, Bulindi, Kyegegwa, Bukedea, Bulambuli, Apac and Oyam | Multi-locational trials for the three oil seed commodities established at different sites in the districts of Serere, Tororo, Kaberamaido, Ngetta, Kitgum, Pader, Abi, Kiryandongo, Bulindi, Kyegegwa, Bukedea, Bulambuli, Apac and Oyam | 10000 |  |  | 10000
[5 empty] | Conduct diseases surveillance studies in major sunflower, groundnuts and sesame agroecologies | Prevalence and distribution of the new virus like disease of suflower established. Disease ditribution maps of major diseases of groundnuts and sesame availed | 28000 | New data collection tools designed and pretested. Information on disease adistribution from two regions collected. | Survelience studies are yet to be conducted starting with the eastern and Northern regions | 8000 |  |  | Data sets from two regions collected, cleaned, analyzed and a preliminary report written | 6000 | Disease distribution map for the virus like disease of sunflower will be generated. |  | 6000 |  | Information on disease distribution in Southern, Central and Western Uganda collected | 8000 | Laboratory analysis is on-going at Makerere Univisersity Kabanyolo Biotechnology laboratory | Disease didtrubition map generated and laboroatory analysis to identify the pathen is on-going | 0 |  |  | 6000
[5 empty] | Collection of diseased plant tisues, culturing, DNA/RNA extraction, sequencing and analysis | Cause of the new virus- like disease symptom in sunflower established | 28000 | Collected and processed (DNA/RNA extraction) of 25 diseased plant tissues from 2 regions (Northern & Eastern) Uganda | Not achieved | 12000 | 12000 | By the time of reporting the sample collection were yet to begin | Sequenced and analysed data from two regions | 10000 | Not done |  | 10000 |  | Collected and processed (DNA/RNA extraction) of 25 diseased plant tissues from 2 regions (Western and Central) | 12000 | No analysis has been done. Isolation and purification still on going | Samplss were collected and pathogen isolation and purification is being done in preparation for DNA extration |  |  | Sequenced, analysed data and pathogen identity confirmed | 10000
[5 empty] | Evaluate the use of inorganic and organic based fertlizers for enhanced groundnuts, sesame and sunflower productivity | The effect of different fertilizer rates and types on groundnuts and sunflower growth yield established | 46000 | Trial to test the effects of different fertilizer rates and combinations on the growth and yield of sesame, sunflower and groundnuts were established | Trials were established in Kiryandongo, Kaberamaido, Kumi, Apac and Abii | 27000 | 27000 |  | Data sets on the performance of groundnuts and sunflower due to fertilizer rates and types recorded | 6000 | Ferlizer trials were established in Kiryandongo, AbiiZARDI, Masindi and Apac districts for the 3 commodities | Yield data collection and harvesting of the 3 commodities is on progress | 6000 |  | Data sets on performance of groundnuts and sunflower due to fertilizer rated and types processed and analysed | 5000 | In Kiryandongo, NaSARRI and Apac, sunflower grain yield increased by 56.4%, 52.2% and 41.2% with the addition of 20N+15Pkg/ha and 60N+7.5Pkg/ha respectively | Some genotypes have been identified for further testing |  | simsim data was lost due to the long dry spell experinced at capsule formation stage in Kiryandongo and Apac districts |  | 8000
[5 empty] | Evaluate different cropping systems for optimal yield and productivity of oil crops (seasame, sunflower and groundnuts) | Intercrops and planting patterns for sesame, sunflower and particular groundnut botanicals identified | 56000 | Trial on planting patterns & intercropping on different for the three comodities (groundnut, sesame and sunflower) were conducted at Tororo datics, Kuju TVC, Lira, Kaberamaido, Kyegegwa, Abii, Serere and Kumi | Trials established onstation and on-farm | 21000 | 22000 |  | Plant growth data sets recorded on the intercropping and planting patterns on groundnut | 18000 | Trials were established in Kiryandongo, AbiiZARDI, Masindi , Apac Tororo Datic Centre, Kaberamaido TVC Ngetta ZARDI, and Kyegegwa District for the 3 commodities | Yield data collection and harvesting of the 3 commodities is on progress | 18000 |  | Data sets from quarter one and two processed and analyzed | 16000 | Trials aimed at upscaling and popularizing the previously Sunflower-legumes intercrops (Sunflower/Soyabeans, Sunflower/Beans, Sunflower/groundnuts, Sunflower/Green grams and Sunflower/Cowpeas) were established. At sametime, sesame and groundnuts trials on plant population were also established and data analysis is on-going | Identified the most suitable intercrops and plant population for groundnuts |  |  |  | 500
|  |  |  | Research extension interface promoted and strengthened | Multiplication of foundation seed of groundnuts, sesame and sunflower varieties | 5 tones of sunflower, 1 tone of groundnuts and 1 tone of sesame foundation seed produced | 78000 | 32 acres of sunflower, 4 acres of groundnuts and 6 acres of sesame planted for foundation seed production | 30acres of sunflower, 4 acres of groundnuts and 5 acres of sesame planted for foundation seed production | 40000 | 38000 | The long dry spell is affecting the crop in the field and yet there was very good germination and crop establishment | Proper agronomic , pest and disease control practices conducted to ensure good harvest | 15000 | Harvesting of the multiplication fields is on-going | 30acres of sunflower, 4 acres of groundnuts and 5 acres of sesame planted for foundation seed production | 15000 |  |  | 23000 | 28 acres of sunflower, 4 acres of groundnuts and 5 acres of sesame planted for foundation seed production | Collectively, we produced 262Kg of breeder seed of groundnuts (Serenut 8, Serenut 11 Serenut 14, DOK1 and DOK2) And 4.2 tonnes of foundation seed for the three commodities
[5 empty] | Production of Dissemination materials (factsheets and information bulletins) | Two information bulletins, 3 factsheets and two brochures developed and printed | 15000 | Drafting of and reciew of factsheets, brochures and bulletin | One draft pull-up and 2 facts each on sesame and sunflower designed and are being revieved | 2000 | 0 |  | Typesetting and procurement of the service providers | 3000 | Reviewed and edited the dissemination materials (factsheet and pull-up) | A pull-up and fact sheet on sesame and sunflower designed sent to press for printing | 3000 |  | Printing and distribution of factsheets, brochures and bulletin | 10000 | Not printed
|  | Dry lands Oilseeds |  | Agricultural research capacity strengthened | Extension staff and other partners trained in improved sunflower and sesame technologies | Extension staff and other partners trained in improved sunflower and sesame technologies | 25000 | Extension staff and other partners trained in improved sunflower and sesame technologies |  | 0 |  | Activity to be undertaken in the next Quarter | Extension staff and other partners trained in improved sunflower and sesame technologies | 25000 | Trainned farmers groups and extension staff from Kiryandongo and lira on sunflower production. | Two farmer groups trainned | 25000 |  | Extension staff and other partners trained in improved sunflower and sesame technologies | 6000 | Extension staff and other partners trained in improvedsunflower and sesame technologies | we trained individual farmers and farmer groups on a number of aspects in the oil seed value chain ranging from production to marketing |  |  | Extension staff and other partners trained in improvedsunflower and sesame technologies | 6000
[5 empty] | Vehicle maintenance ((UG 2320A ) | Vehicles((UG 2320A ) maintained | 15000 | All tyres tyres of replaced and vehicle insured | Major repairs done autotune and the vehicle is ready back on the road | 13000 | 3800 |  | Minor repairs and services done | 1000 |  |  |  |  | Vehicles fully sercived and minor repairs executed | 3000 | Minor repairs and services done |  |  |  | Minor repairs and services done | 1000
| Off budget grants (IFAD Project) | Oilcrops Programme | Enhancing institutional breeding capacity in Ghana, Senegal and Uganda to develop climate resilient crops for African smallholder farmers | Generation of agricultural technologies | Delivery chain and knowledge platform | Plant 6 NPT sites identified; 2)multiplication of breeder and foundation seed for at least 6 different flagship varieties | 50000 | Plant 6 NPT sites identified; 2)6 acre land for multiplication of breeder and foundation seed for at least 6 different flagship varieties has also be prepared on station at NaSARRI. | 1)Land for National Performance Trials (NPT) prepared at the following sites Northern Uganda (Ngetta ZARDI, Abi ZARDI, Pader TVC), Western Uganda (Bulindi ZARDI, Rwebitaba ZARDI), Eastern Uganda (Nakabango TVC, Buginyanya, NaSARRI) for evaluating mother trials (NPTs) ; 2) 6 acre prepared for Breeder Seeds Production |  |  |  | 1)Land for National Performance Trials (NPT) prepared at the following sites Northern Uganda (Ngetta ZARDI, Abi ZARDI, Pader TVC), Western Uganda (Bulindi ZARDI, Rwebitaba ZARDI), Eastern Uganda (Nakabango TVC, Buginyanya, NaSARRI) for evaluating mother trials (NPTs) ; 2) 6 acre prepared for Breeder Seeds Production | 10000 | 1)Land for National Performance Trials (NPT) prepared at the following sites Northern Uganda (Ngetta ZARDI, Abi ZARDI, Pader TVC), Western Uganda (Bulindi ZARDI, Rwebitaba ZARDI), Eastern Uganda (Nakabango TVC, Buginyanya, NaSARRI) for evaluating mother trials (NPTs) ; 2) 6 acre prepared for Breeder Seeds Production | 1)Land for National Performance Trials (NPT) prepared at the following sites Northern Uganda (Ngetta ZARDI, Abi ZARDI, Pader TVC), Western Uganda (Bulindi ZARDI, Rwebitaba ZARDI), Eastern Uganda (Nakabango TVC, Buginyanya, NaSARRI) for evaluating mother trials (NPTs) ; 2) 6 acre prepared for Breeder Seeds Production | 10000
[5 empty] | Improved data management and digitalising breeding | Digitalization of Breeding process at naSARRI | 10000 | Assemle germplasm list for importation into BMS; 2)Enter nursery trial into BMS;3)Generate and collect all NPT data in BMS; 4)Identify BMS focal person for NaSARRI | 1)Groundnut germplasm lists are ready for importation into BMS.2)Nursery trials is entered and conducted in BMS,3)All experiments onstation and at NPT sites are designed in BMS and the data will be collected using tablets, 4) BMS focal person for NaSARRI identified as Mr Moses Otuba Amugoli. | 10000 |  |  | 1)Groundnut germplasm lists are ready for importation into BMS.2)Nursery trials is entered and conducted in BMS,3)All experiments onstation and at NPT sites are designed in BMS and the data will be collected using tablets, 4) BMS focal person for NaSARRI identified as Mr Moses Otuba Amugoli. | 5000 | 1)Groundnut germplasm lists are ready for importation into BMS.2)Nursery trials is entered and conducted in BMS,3)All experiments onstation and at NPT sites are designed in BMS and the data will be collected using tablets, 4) BMS focal person for NaSARRI identified as Mr Moses Otuba Amugoli. | 1)Groundnut germplasm lists are ready for importation into BMS.2)Nursery trials is entered and conducted in BMS,3)All experiments onstation and at NPT sites are designed in BMS and the data will be collected using tablets, 4) BMS focal person for NaSARRI identified as Mr Moses Otuba Amugoli. | 5000
[5 empty] | integrating modern breeding approaches | Germplasm collection for African reference set development; Breeding Perfomace Assessment Tool undertaken | 40000 | 1)Assemble germplasm for genotyping; 2)Process import permit for germplasm shipments; 3)Plan for a detailed BPAT Assessment | · Germplasm (both local and elite) for reference set sent to Senegal and USA for genotyping.2)· Together with sister projects PMIL and TLIII, preliminary BPAT assessment was done and a consultant is being hired to do a detailed one soon | 20000 |  |  | 1)Assemble germplasm for genotyping; 2)Process import permit for germplasm shipments; 3)Plan for a detailed BPAT Assessment | 8000 | 1)Assemble germplasm for genotyping; 2)Process import permit for germplasm shipments; 3)Plan for a detailed BPAT Assessment | 1)Assemble germplasm for genotyping; 2)Process import permit for germplasm shipments; 3)Plan for a detailed BPAT Assessment | 8000
[5 empty] | Capacity enhancement (human and infrastructure) | Instal irrigation facility for 10 acre plot at NaSARRI | 15000 | Initiate the procurement process for installation of a functional Irrigation system at NaSARRI for 10 acre plot | Irrigation system installation process initiated at NaSARRI | 15000 |  |  | Irrigation system with reserviours up and running by december 2018 | 15000 | Irrigation system with reserviours up and running by december 2018 | Irrigation system with reserviours up and running by december 2018 | 15000
[6 empty] | Train a PhD student in Groundnut Breeding | 70000 | IdentifyPhD student | Student (Ms Achola Esther) registered at MUK andd attending classes | 17500 | 17500 |  | Normal progress and completion of taught courses | 5000 | Normal progress and completion of taught courses | Normal progress and completion of taught courses | 5000
| Off budget grants (TLIII Project) |  | Enhance groundnut productivity and production in drought prone areas of sub-Saharan Africa | Generation of agricultural technologies | Gender
[5 empty] | Breeding | Trait Discovery | 15000 | Irrigation system installed and functional | Ten (10) acres under irrigation |  | 15000 |  | Functional Irrigation scheme on 10 acres. Government adds up other acreages | 15000 | Irrigation system installed and functional | Irrigation system installed and functional | 15000
[7 empty] | 10000 | Superior lines for drought and Aflatoxin tolerant genotypes selected, replanted and screened in 2018A season | Superior lines for drought and Aflatoxin tolerant genotypes selected, replanted and screened, harvested and ready for replanting in 2018B |  |  |  | Superior lines for drought and Aflatoxin tolerant genotypes selected, replanted and screened, harvested and ready for replanting in 2018B | 3000 | Superior lines for drought and Aflatoxin tolerant genotypes selected, replanted and screened, harvested and ready for replanting in 2018B | Superior lines for drought and Aflatoxin tolerant genotypes selected, replanted and screened, harvested and ready for replanting in 2018B | 3000
[7 empty] | 15000 | GRD and LLS mapping Populations from ICRISAT evaluated in two LLS hotspot sites in 2018A and B | Populations not sent from ICRISAT Nairobi |  |  | GRD and LLS mapping Populations from ICRISAT evaluated in two LLS hotspot sites in 2018B | Populations not sent from ICRISAT Nairobi | 6000 | Populations not sent from ICRISAT Nairobi | Populations not sent from ICRISAT Nairobi | 6000
[6 empty] | Management and sharing of pedigree, genotyping and phenotyping datasets | 17000 | Alternative Server installed and cloud Storage purchased and hosting data | Additional resources from IBP, USAID for Amazon cloud storage got |  |  |  | Additional resources from IBP, USAID for Amazon cloud storage got | 7000 | Additional resources from IBP, USAID for Amazon cloud storage got | Additional resources from IBP, USAID for Amazon cloud storage got | 7000
Breeding pipeline
[6 empty] | Develop short duration (SD) breeding lines with moderate levels of resistance to LLS | 13000 | Release NaSARRI Short duration lines which passed NDUS test and have enough seeds (DOK 1T, DOK1R).Lines with less seeds (SGV –ER 10010) bulked for release in 2018B/2019A | Data and report ready. Awaiting scheduling of the variety release committee sitting |  |  | Bulking to enough quantity of the seeds of the released | Data and report ready. Awaiting scheduling of the variety release committee sitting | 4000 | Data and report ready. Awaiting scheduling of the variety release committee sitting | Data and report ready. Awaiting scheduling of the variety release committee sitting | 4000
[6 empty] | Develop SD + drought tolerance (10 lines) and SD + high oil (10 lines), | 16000 | Multilocation evaluation of short duration lines derived from Gwerinut x S.2 red (4 test lines; SGV 0060, SGV 0050, SGV 0062, SGV 0049), Gwerinut x S.2 tan (4 test lines; SGV 0083, SGV 0082, SGV 0072, SGV 0076), S.3 x Erudu red (4 test lines; SGV –ER 10010, SGV –ER 10004, SGV –ER 10002, SGV –ER 10003); Acholi white x Igola/S6T advanced crosses | Onstation and offstations harvest brought to NaSARRI store, postharvest data taken and seeds prepared for 2018B planting for further evluation |  |  |  | Multilocation evaluation of short duration lines derived from Gwerinut x S.2 red (4 test lines; SGV 0060, SGV 0050, SGV 0062, SGV 0049), Gwerinut x S.2 tan (4 test lines; SGV 0083, SGV 0082, SGV 0072, SGV 0076), S.3 x Erudu red (4 test lines; SGV –ER 10010, SGV –ER 10004, SGV –ER 10002, SGV –ER 10003); Acholi white x Igola/S6T advanced crosses | 6000 | Multilocation evaluation of short duration lines derived from Gwerinut x S.2 red (4 test lines; SGV 0060, SGV 0050, SGV 0062, SGV 0049), Gwerinut x S.2 tan (4 test lines; SGV 0083, SGV 0082, SGV 0072, SGV 0076), S.3 x Erudu red (4 test lines; SGV –ER 10010, SGV –ER 10004, SGV –ER 10002, SGV –ER 10003); Acholi white x Igola/S6T advanced crosses | Multilocation evaluation of short duration lines derived from Gwerinut x S.2 red (4 test lines; SGV 0060, SGV 0050, SGV 0062, SGV 0049), Gwerinut x S.2 tan (4 test lines; SGV 0083, SGV 0082, SGV 0072, SGV 0076), S.3 x Erudu red (4 test lines; SGV –ER 10010, SGV –ER 10004, SGV –ER 10002, SGV –ER 10003); Acholi white x Igola/S6T advanced crosses | 6000
[6 empty] | Evaluation of SD ICRISAT Introduction. | 11000 | characterize the 17 introductions onstation | Onstation characterization done for first season. Seeds prepared for 2018B evaluations |  |  | 2018B characterization of the 17 ICRISAT lines | Onstation characterization done for first season. Seeds prepared for 2018B evaluations | 2000 | Onstation characterization done for first season. Seeds prepared for 2018B evaluations | Onstation characterization done for first season. Seeds prepared for 2018B evaluations | 20000
[6 empty] | Develop ten (10) medium duration breeding lines (high levels of LLS resistance and GRD and other stresses | 10000 | Evaluate 10 Medium Duration (MD lines) for the last time at NPT sites pipelines :89751 X S.1 (SGV 0029,SGV 0019,SGV 0023,SGV 0002); 91707 X S.1 ( SGV 07003, SGV 07002, SGV 07008, SGV 07005 | 10 Medium Duration (MD lines) evaluated for the last time at NPT sites pipelines :89751 X S.1 (SGV 0029,SGV 0019,SGV 0023,SGV 0002); 91707 X S.1 ( SGV 07003, SGV 07002, SGV 07008, SGV 07005 |  |  |  | Evaluate 10 Medium Duration (MD lines) for the last time at NPT sites pipelines :89751 X S.1 (SGV 0029,SGV 0019,SGV 0023,SGV 0002); 91707 X S.1 ( SGV 07003, SGV 07002, SGV 07008, SGV 07005 | 5000 | Evaluate 10 Medium Duration (MD lines) for the last time at NPT sites pipelines :89751 X S.1 (SGV 0029,SGV 0019,SGV 0023,SGV 0002); 91707 X S.1 ( SGV 07003, SGV 07002, SGV 07008, SGV 07005 | Evaluate 10 Medium Duration (MD lines) for the last time at NPT sites pipelines :89751 X S.1 (SGV 0029,SGV 0019,SGV 0023,SGV 0002); 91707 X S.1 ( SGV 07003, SGV 07002, SGV 07008, SGV 07005 | 5000
[6 empty] | Develop five confectionery lines resistant to LLS and GRD with improved nutrition for Uganda | 8000 | Evaluate for 13 NaSARRI confectionary lines at NPT | NPT evaluation for 13 NaSARRI confectionary lines |  |  | Evaluate for 13 NaSARRI confectionary lines at NPT | Evaluate for 13 NaSARRI confectionary lines at NPT | 3000 | Evaluate for 13 NaSARRI confectionary lines at NPT | Evaluate for 13 NaSARRI confectionary lines at NPT | 3000
[6 empty] | Four to five superior breeding lines (arising from multi-location testing) identified in Uganda each year. | 14000 | Identify four to five superior breeding lines (arising from multi-location testing). | 16 superior lines identified from (91707 x Serenut 1R; 89751 x Serenut 1R; Serenut 3 X Erudu red; Gwerinut X Serenut 2) undergoing FPVS, onfarm and NPTs and at least three selections submitted for DUS tests in the 2018B season. |  |  | Identify four to five superior breeding lines (arising from multi-location testing). | Identify four to five superior breeding lines (arising from multi-location testing). | 5000 | Identify four to five superior breeding lines (arising from multi-location testing). | Identify four to five superior breeding lines (arising from multi-location testing). | 5000
[5 empty] | Seeds systems | Release of 8-10 tons breeder seed of at least one best bet variety in Uganda produced each year. | 9000 | Produce 4-5 tons breeder seed of at least one best bet variety in Uganda produced each season. | 4tons of breeder seeds harvested by partners and onstation |  |  | Produce 4-5 tons breeder seed of at least one best bet variety in Uganda produced each season. | Produce 4-5 tons breeder seed of at least one best bet variety in Uganda produced each season. | 5000 | Produce 4-5 tons breeder seed of at least one best bet variety in Uganda produced each season. | Produce 4-5 tons breeder seed of at least one best bet variety in Uganda produced each season. | 5000
[6 empty] | 267 t of Basic seed produced in Uganda throughout project life | 12000 | Produce atleast 85T basic seed produced in collaboration with partners (seed companies, individual farmers/groups). | 85T basic seed produced in collaboration with partners (seed companies, individual farmers/groups). |  |  |  | Produce atleast 85T basic seed produced in collaboration with partners (seed companies, individual farmers/groups). | 4000 | Produce atleast 85T basic seed produced in collaboration with partners (seed companies, individual farmers/groups). | Produce atleast 85T basic seed produced in collaboration with partners (seed companies, individual farmers/groups). | 4000
[6 empty] | Popularizing new varieties | 7500 | 1000 Copies of seed production, postharvest, seed business management guides produced and shared with partners annually in all participating countries for each crop |  |  | Not done due to shortage of money | Produce atleast 85T basic seed produced in collaboration with partners (seed companies, individual farmers/groups). | 1000 Copies of seed production, postharvest, seed business management guides produced and shared with partners annually in all participating countries for each crop | 7500 | 1000 Copies of seed production, postharvest, seed business management guides produced and shared with partners annually in all participating countries for each crop | 1000 Copies of seed production, postharvest, seed business management guides produced and shared with partners annually in all participating countries for each crop | 7500
[7 empty] | 12000 | Electronic (TV, radio) programs per crop (ESA-GN: 3) and print media (ESA-GN: 3] disseminated annually and per country. |  | 5 Electronic (TV, radio) programs and 4 print media feature. |  | Electronic (TV, radio) programs per crop (ESA-GN: 3) and print media (ESA-GN: 3] disseminated annually and per country. | Electronic (TV, radio) programs per crop (ESA-GN: 3) and print media (ESA-GN: 3] disseminated annually and per country. | 6000 | Electronic (TV, radio) programs per crop (ESA-GN: 3) and print media (ESA-GN: 3] disseminated annually and per country. | Electronic (TV, radio) programs per crop (ESA-GN: 3) and print media (ESA-GN: 3] disseminated annually and per country. | 6000
[7 empty] | 9000 | Attend National Agricultural fairs in jinja | Particpated in the 2018 Source of the Nile agricultural Show where we had both demonstration plots and Products and dissemination materials at the stalls
| Off budget grants (ICIPE FINGER MILLET Project) | Dryland Cereals | Partnership to deliver to market Striga weed resistant maize and finger millet varieties in Kenya and Uganda | Generation of agricultural technologies | Evaluation of finger millet lines for resistance to Striga | 2 Striga resistant finger millet lines identified | 16000 | 25 finger millet lines planted in natural striga infested land in Pallisa, Kumi, Amolatar and Kitgum | Data recorded on number of striga plants, plant height recorded in Kumi, Pallisa, Amolatar and Kitgum | 6000 | 6000 | Delay in data recording due to borrowing of funds by other projects and delay in paying back. | Data on striga plants and finger millet summarrized and analysed | 2000 | Number of striga plants ranged from 31-245 in Pallisa, 0-26 in Kumi, 0-8 in Amolatar and 9-76 in Kitgum. Finger millet grain yield range from 315-1412 in Pallisa, 169-923 in Kumi, 478-1463 in Amolatar and 509-1239 kg/ha. | Based on this preliminary data, 5 genotypes have showed good tolerance to high striga weed infestation (80 strigaplants/1.6 m2). | 4000 | Drought affected the grain yield especially in Kumi. | 16 finger millet lines planted in natural striga infested land in Pallisa, Kumi and Namutumba | 5000 | Farmers striga infested fields 4, selected in Kumi, Pallisa, Amolatar and Kitgum. Seed of 16 genotypes packed | Awaits the planting of 16 striga NPT in farmers fields in mid April |  | Delay in coming back of the rains | Data on Striga and finger millet plants recorded, summarised and analysed | 3000
|  |  |  | Generation of agricultural technologies | Finger millet seed with resistance to striga multiplied | 100 kg of Nucleus seed produced | 6000 | 0.5 acre of land ploughed and planted | 0.1 acre of NAROMIL4 was harvested. Finger millet 60 D from Kenya was not multiplied | 2000 | 2000 | The striga resistant variety D 60 was still under mulplication in Kenya. | NAROMIL4 threshed and weighed | 1000 | A total of 14 kg of NAROMIL 4 and others of NAROMIL 1,2,3,5 gave 7 kg was obtained from 10x10m plot . | 60 D is under multiplication at Maseno University, Kenya | 2000 |  | 1 acre of NAROMIL 4 and 1 acre of 60 D finger millet varieties ploughed and planted | 2000 | At NaSARRI, 12 acres of land bush cleared and first ploughing done. 5 NAROMIL varieties prepared for multiplication | 5 NAROMIL varieties to be multiplied |  | A waits second ploughing and planting | Varieties harvested, threshed and weighed. 100 kg of NAROMIL 4 and 100 kg of 60 D produced | 1000
|  |  |  | Generation of agricultural technologies | Finger millet on-farm demonstration plots established | Striga finger millet resistant variety promoted | 8000 | Released Striga finger millet resistant varieties planted in Pallisa, Kumi, Lira and Kitgum | Demostrations for striga resitant varieties not established. | 2000 | 2000 | Striga finger millet resistant varieties under multiplication | Demostrations for striga resitant varieties not established. | 2000 | Striga finger millet resistant varieties under multiplication | Demostrations of finger millet resistant varieties was not established | 2000 | Drought affected the grain yield in NaSARRI. | Demonstrations of Striga resistant and other released varieties planted in farmers fields in Pallisa, Kumi, Amolatar, Kitgum and Abbi | 1000 | 4 farmers fields for establishement of demonstrations selected in Pallisa, Kumi, Amolatar and Kitgum | Awaits the planting of demostrations in mid April |  | Delay in coming back of the rains
| CGS- GOU |  |  |  | collection of sorghum germplasm | atleast 100 sorghum germplasm collected |  | 108 germplasm collected | 108 sorghum germplasm collected
[5 empty] | field characterisation of germplasm for low tanin trait | atleast 100 sorghum germplasm characterised for low tanin trait |  | land for field trial prepared | land ws cleared and 1st and 2nd ploughing done | [5 empty] | germplasm characterisation trial established | trials were planted, weeded, thined and data collection on going |  |  | germplasm characterised for low tanin trait |  | trial harvested | data anlysed and 12 best perfoming lines selectet for MLT | 4944
[19 empty] | 2240010 |  | medical and vetinary |  | 1243.75
[19 empty] | 2111020 |  | contract labor |  | 3000
[19 empty] | 2210010 |  | Advertisement |  | 700
[5 empty] | adaptive research for sorghum with low tanin | atleast 10 lines with low tanin trait advanced to MLT | [12 empty] | 12 lines tested for adaptability under NPT |  | site selection conducted | 10 sites were selected for NPT and land was prepared. | 14093
[5 empty] | establishment of demos | 3 demo sites established | [12 empty] | 2210030 |  | Training |  | 2380
[5 empty] | development of information materials | [13 empty] | 2250010 |  | consultancy |  | 1976.75
[5 empty] | printing of sorghum infromation materials | [13 empty] | 2270010 |  | travel |  | 1655.5
[19 empty] | 2270040 |  | Fuel, lubricants and oils |  | 2080.25
|  |  |  | OBT Performance Challenges | [14 empty] | 2240060 |  | Agric supplies |  | 6000